## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED HARINCHAOWRA PWSS COOCHBEHAR 1 BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/15933 | Augmentation | Execution of different works related to AUG. of HARINCHAOWRA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000815/2022-2023 | 1997 | 28/03/2023 | 17/03/2025 | MATRI ENTERPRISEES | 272.18 | 143.06 | 52.56 | 40
2 | COOCHBEHAR |  | Northern Mechanical Division II | AUGUMENTATION OF GROUND WATER BASED HARINCHAOWRA PWSS COOCHBEHAR 1 BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/15933 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Harinchowra Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001100/2023-2024 | 2833/NMD-II | 12/10/2023 | 11/11/2023 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 18.5 | 7.33 | 39.6 | 50
3 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED HARINCHAOWRA PWSS COOCHBEHAR 1 BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/15933 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 107/CD | 26/04/2023 | 26/04/2023 | Resource Division | 29.03 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED HARINCHAOWRA PWSS COOCHBEHAR 1 BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/15933 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
5 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED HARINCHAOWRA PWSS COOCHBEHAR 1 BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/15933 | Augmentation | Hiring of Diesel Vehicle for MTB Assistant Engineer for inspection of site checking of FHTC and LDS, searching of land for different PWSS under Cooch Behar Division, PHE Dte. (From 01-07-24 to 30-06-2025). | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000464/2024-2025 | 1236/CD | 29/06/2024 | 29/06/2025 | SIDHARTHA ROY | 1.92 | 0 | 0 | 50
6 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED HARINCHAOWRA PWSS COOCHBEHAR 1 BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/15933 | Augmentation | Execution of different works (WITHIN HARINCHAOWRA & BOGDABARI KESAIBARI AREA) related to JIRANPUR PWSS under JAL JEEVAN MISSION P B | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000679/2024-2025 | 1184/CD | 18/06/2024 | 13/06/2025 | MALAY KR.DEB | 66.85 | 0 | 0 | 35
7 | COOCHBEHAR |  | Northern Mechanical Division II | AUGUMENTATION OF GROUND WATER BASED HARINCHAOWRA PWSS COOCHBEHAR 1 BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/15933 | Augmentation | NEW SERVICE CONNECTION CHARGES AT HARIN CHOWRA (AUG) PWSS, PH-I |  |  | BILL/00197/2024-2025 | BP-52/24-25 | 29/04/2024 | 29/04/2024 | WBSEDCL | 6.12 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED HARINCHAOWRA PWSS COOCHBEHAR 1 BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/15933 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000100/2025-2026 | 729/CD | 17/05/2025 | 15/08/2025 | MS BIDYUT SARKAR | 23.91 | 0 | 0 | 0
9 | COOCHBEHAR |  | Northern Mechanical Division II | AUGUMENTATION OF GROUND WATER BASED HARINCHAOWRA PWSS COOCHBEHAR 1 BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/15933 | Augmentation | NEW SERVICE CONNECTION AT HARINCHOWRA (AUG) PH-II |  |  | BILL/02031/2024-2025 | BP-457/24-25 | 09/01/2025 | 09/01/2025 | WBSEDCL | 5.13 | 0 | 0 | 0
Total | [13 empty] | 20212.93 | 150.38 | 0.74