## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Execution of different works related to CHAKCHAKA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000454/2022-2023 | 3430/CD | 29/12/2022 | 28/01/2023 | DAS ENTERPRISE | 2.42 | 2.42 | 99.97 | 100
2 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | joining of pipe line construction of street stand post and other allied works under Chakchaka PWSS under Cooch Behar Sadar Sub-Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000569/2021-2022 | 721/SD | 18/03/2022 | 02/04/2022 | M/S. MANDAL CONSTRUCTION | 1.3 | 0 | 0 | 1
3 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Water supply arrangement, provision for cycle stand, colour washing etc. at chakchaka botting plant under Chakchaka WSS, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000577/2021-2022 | 718/SD | 18/03/2022 | 02/04/2022 | M/S. MANDAL CONSTRUCTION | 4.38 | 0 | 0 | 1
4 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Dinhata-II Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000826/2022-2023 | 2046/CD | 31/03/2023 | 31/05/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 20
5 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Execution of different works related to AUG. of CHAKCHAKA ZONE-I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000113/2023-2024 | 666/CD | 14/07/2023 | 11/12/2023 | SUMI ENTERPRISE | 329.74 | 139.15 | 42.2 | 30
6 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Name of Work: Execution of different works related to KHAGRABARI PWSS under JAL JEEVAN MISSION PART B | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000253/2023-2024 | 1020/CD | 22/09/2023 | 21/11/2023 | MS SSB CONSTRUCTION CO | 73.68 | 68.4 | 92.82 | 100
7 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Name of Work: Execution of different works related to KHAGRABARI AREA adjacent to CHAKCHAKA PWSS under JAL JEEVAN MISSION PART N | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000255/2023-2024 | 1022/CD | 22/09/2023 | 21/11/2023 | BIJOY ROY | 49.45 | 40 | 80.89 | 99
8 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Name of Work: Execution of different works related to CHAKCHAKA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000256/2023-2024 | 1024/CD | 22/09/2023 | 21/11/2023 | AASHIRBAD ENTERPRISE | 16.96 | 12.69 | 74.83 | 100
9 | COOCHBEHAR |  | Northern Mechanical Division II | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Chakchaka Water Supply Scheme TW No.-I of Zone-I under NMD-II,PHE.Dte,,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001080/2023-2024 | 2777/NMD-II | 05/10/2023 | 04/11/2023 | HARAGOURI ENTERPRISE | 10.53 | 8.6 | 81.67 | 60
10 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Execution of different works related to CHAKCHAKA Z I&II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000395/2023-2024 | 1367/CD | 05/12/2023 | 29/03/2025 | M/S. MANDAL CONSTRUCTION | 96.19 | 88.23 | 91.73 | 67
11 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Execution of different works related to CHAKCHAKA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000051/2023-2024 | 452/CD | 31/05/2023 | 30/06/2023 | M/S. MANDAL CONSTRUCTION | 5.48 | 5.08 | 92.77 | 100
12 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Surveying door to door to collect information regarding Jal Jeevan Mission of Cooch Behar-I Block (Part -A) under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000236/2023-2024 | 899/CD | 31/08/2023 | 15/09/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
13 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Surveying door to door to collect information regarding Jal Jeevan Mission of Dinhata-II Block (Part-B) under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000243/2023-2024 | 906/CD | 31/08/2023 | 15/09/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
14 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Surveying door to door to collect information regarding Jal Jeevan Mission of Mekhliganj Block under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000249/2023-2024 | 912/CD | 31/08/2023 | 15/09/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
15 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Surveying door to door to collect information regarding Jal Jeevan Mission of Sitai Block under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000250/2023-2024 | 913/CD | 31/08/2023 | 15/09/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
16 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-I Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000198/2023-2024 | 521/CD | 21/06/2023 | 20/08/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
17 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-II Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000199/2023-2024 | 522/CD | 21/06/2023 | 20/08/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
18 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-I Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000200/2023-2024 | 523/CD | 21/06/2023 | 20/08/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
19 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-II Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000201/2023-2024 | 524/CD | 21/06/2023 | 20/08/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
20 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 134/CD | 27/04/2023 | 27/04/2023 | Resource Division | 132.89 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Execution of different works related (Within area of CHAKCHAKA Z II) to HASTABUD KASALDANGA & CHAKCHAKA ZONE I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000086/2024-2025 | 1190/CD | 24/06/2024 | 19/09/2025 | SWAPAN KR.SARKAR | 96.7 | 44.08 | 45.59 | 95
22 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
23 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO Chakchaka PWSS UNDER JAL JEEVAN MISSION. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000540/2024-2025 | 2224/CD | 23/12/2024 | 21/05/2025 | DAS AND COMPANY | 7.4 | 0 | 0 | 50
24 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | HIRING VEHICLE FOR AE/HQ |  |  | BILL/00535/2024-2025 | BP-217 | 31/07/2024 | 31/07/2024 | ANIMESH DHAR CHOUDHURY | 0.73 | 0 | 0 | 0
25 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
26 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | EXECUTION OF DIFFERENT WORK AT MANTANI PWSS |  |  | BILL/02074/2023-2024 | BP-494 | 02/03/2024 | 02/03/2024 | SWAPAN SAHA | 5.55 | 0 | 0 | 0
27 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION |  |  | ORD/000050/2025-2026 | 705/CD | 17/05/2025 | 15/08/2025 | MS SSB CONSTRUCTION CO | 32.51 | 0 | 0 | 0
28 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/15934 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000097/2025-2026 | 699/CD | 17/05/2025 | 13/11/2025 | SANKAR BANIK | 25.58 | 0 | 0 | 30
Total | [13 empty] | 20745.32 | 417.5 | 2.01