## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Retrofitting works of NATABARI (Part-A) PWSS under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000091/2022-2023 | 299/CD | 31/05/2022 | 15/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.98 | 4.98 | 100 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Retrofitting works of NATABARI (Part-C) PWSS under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000093/2022-2023 | 301/CD | 31/05/2022 | 15/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.97 | 4.97 | 100 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Retrofitting works of NATABARI (Part-B) PWSS under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000092/2022-2023 | 300/CD | 31/05/2022 | 15/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.95 | 3.95 | 100 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Retrofitting works of NATABARI (Part-D) PWSS under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000094/2022-2023 | 302/CD | 31/05/2022 | 15/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.98 | 4.98 | 100 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000124/2023-2024 | 218/CD | 27/04/2023 | 27/04/2023 | Resource Division | 12.39 | 0 | 0 | 0
6 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Natabari Pwss | SM/15935 | Augmentation | New service connection at Natabari pwss |  |  | BILL/02146/2023-2024 |  | 01/12/2023 | 01/12/2023 | WBSEDCL | 6.43 | 0 | 0 | 0
7 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Natabari Pwss | SM/15935 | Augmentation | QUOTATION FOR NSC AT NATABARI PH NO III |  |  | BILL/01059/2023-2024 |  | 28/07/2023 | 28/07/2023 | WBSEDCL | 4.92 | 0 | 0 | 0
8 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Natabari Pwss | SM/15935 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT NATABARI PWSS TW NO -III |  |  | BILL/01421/2023-2024 |  | 16/08/2023 | 16/08/2023 | WBSEDCL | 4.92 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | quotation for new service connection natabari pwss t/well no 1 |  |  | BILL/01308/2023-2024 | BP-1036 | 13/02/2024 | 13/02/2024 | WBSEDCL | 6.43 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Providing FHTC & New laying UPVC/DI GI Pipe line construction of Sluice valve chamber & other allied works at NATABARI PWSS under Cooch Behar Division, PHED (PART ¿B) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000263/2021-2022 | 933/CD | 31/12/2021 | 30/04/2022 | SHREE RANI SATI ENTERPRISE | 155.23 | 7.3 | 4.7 | 20
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Providing FHTC and Laying of Pipe Line & Other allied work at NATABARI PWSS under JAL JEEVAN MISSION Part-F | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000220/2022-2023 | 709/CD | 27/08/2022 | 21/08/2025 | SHREE RANI SATI ENTERPRISE | 93.75 | 79.37 | 84.66 | 90
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Providing FHTC and Laying of Pipe Line & Other allied work at NATABARI PWSS under JAL JEEVAN MISSION Part-E | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000219/2022-2023 | 708/CD | 27/08/2022 | 19/08/2025 | SHREE RANI SATI ENTERPRISE | 94.17 | 78.21 | 83.05 | 90
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Constructions of HWS & 2nd Site P.House, B.Wall, Sinking T/Well & Other allied works at AUG. of NATABARI PWSS under Tufanganj Sub- Divn., PHE Dte. Within Cooch Behar Division, PHE Dte. Under JJM Programme. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000035/2023-2024 | 372/CD | 23/05/2023 | 02/10/2025 | SHREE RANI SATI ENTERPRISE | 51.38 | 34.33 | 66.82 | 40
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
15 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO Natabari Bajejama Chilakhana ZONE-I Chhatoa PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000546/2024-2025 | 2231/CD | 23/12/2024 | 20/08/2025 | AASHIRBAD ENTERPRISE | 27.56 | 0 | 0 | 80
16 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO Natabari Bajejama Chilakhana Zone-III B CHILAKHANA Z 3PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000587/2024-2025 | 2270/CD | 23/12/2024 | 22/04/2025 | HARIDAS GHOSH | 36.27 | 0 | 0 | 100
17 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000029/2025-2026 | 717/CD | 17/05/2025 | 15/08/2025 | UTPAL CHAKRABORTY | 14.38 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO Natabari & CHHAT RAMPUR PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000543/2024-2025 | 2227/CD | 23/12/2024 | 21/02/2025 | UTTAM SAHA | 20.32 | 4.66 | 22.91 | 100
19 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000025/2025-2026 | 713/CD | 17/05/2025 | 15/08/2025 | UTPAL CHAKRABORTY | 18.29 | 0 | 0 | 100
Total | [13 empty] | 20354.6 | 222.74 | 1.09