## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Providing FHTC and Laying of Pipe Line & Other allied work at NATABARI PWSS under JAL JEEVAN MISSION Part-F | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000220/2022-2023 | 709/CD | 27/08/2022 | 11/10/2022 | SHREE RANI SATI ENTERPRISE | 93.75 | 55.23 | 58.91 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Providing FHTC and Laying of Pipe Line & Other allied work at NATABARI PWSS under JAL JEEVAN MISSION Part-E | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000219/2022-2023 | 708/CD | 27/08/2022 | 11/10/2022 | SHREE RANI SATI ENTERPRISE | 94.17 | 53.57 | 56.88 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Retrofitting works of NATABARI (Part-A) PWSS under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000091/2022-2023 | 299/CD | 31/05/2022 | 15/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.98 | 4.98 | 100 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Retrofitting works of NATABARI (Part-C) PWSS under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000093/2022-2023 | 301/CD | 31/05/2022 | 15/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.97 | 4.97 | 100 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Retrofitting works of NATABARI (Part-B) PWSS under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000092/2022-2023 | 300/CD | 31/05/2022 | 15/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.95 | 3.95 | 100 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Retrofitting works of NATABARI (Part-D) PWSS under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000094/2022-2023 | 302/CD | 31/05/2022 | 15/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.98 | 4.98 | 100 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000124/2023-2024 | 218/CD | 27/04/2023 |  | Resource Division | 12.39 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Constructions of HWS & 2nd Site P.House, B.Wall, Sinking T/Well & Other allied works at AUG. of NATABARI PWSS under Tufanganj Sub- Divn., PHE Dte. Within Cooch Behar Division, PHE Dte. Under JJM Programme. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000035/2023-2024 | 372/CD | 23/05/2023 | 22/07/2023 | SHREE RANI SATI ENTERPRISE | 51.38 | 0 | 0 | 0
9 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Natabari Pwss | SM/15935 | Augmentation | QUOTATION FOR NSC AT NATABARI PH NO III |  |  | BILL/01059/2023-2024 | null | 28/07/2023 |  | WBSEDCL | 4.92 | 0 | 0 | 0
10 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Natabari Pwss | SM/15935 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT NATABARI PWSS TW NO -III |  |  | BILL/01421/2023-2024 | null | 16/08/2023 |  | WBSEDCL | 4.92 | 0 | 0 | 0
11 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Natabari Pwss | SM/15935 | Augmentation | New service connection at Natabari pwss |  |  | BILL/02146/2023-2024 | null | 01/12/2023 |  | WBSEDCL | 6.43 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | quotation for new service connection natabari pwss t/well no 1 |  |  | BILL/01308/2023-2024 | BP-1036 | 13/02/2024 |  | WBSEDCL | 6.43 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | quotation for new service connection natabari pwss t/well no 1 |  |  | BILL/01308/2023-2024 | BP-1036 | 13/02/2024 |  | WBSEDCL | 6.43 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Natabari Pwss | SM/15935 | Augmentation | Providing FHTC & New laying UPVC/DI GI Pipe line construction of Sluice valve chamber & other allied works at NATABARI PWSS under Cooch Behar Division, PHED (PART ¿B) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000263/2021-2022 | 933/CD | 31/12/2021 | 30/04/2022 | SHREE RANI SATI ENTERPRISE | 155.23 | 0 | 0 | 85
Total | [13 empty] | 20244.2 | 127.67 | 0.63