## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BHERBHERI PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16140 | Augmentation | Execution of different works related to AUG. of Bherbheri PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000810/2022-2023 | 1995 | 28/03/2023 | 25/08/2023 | SHREE RANI SATI ENTERPRISE | 371.75 | 0 | 0 | 40
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BHERBHERI PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16140 | Augmentation | Execution of different works related to AUG. of Bherbheri PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1365/1-5/NBC-1; Dt.: 28-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000634/2022-2023 | 1995/CD | 28/03/2023 | 25/08/2023 | SHREE RANI SATI ENTERPRISE | 371.75 | 0 | 0 | 50
3 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED BHERBHERI PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16140 | Augmentation | ELECTRIC QUOTATION FOR NEW SERVICE CONNECTION AT BHERBHERI TW NO I |  |  | BILL/02689/2023-2024 | BP-2023-24-594 | 08/02/2024 | 08/02/2024 | WBSEDCL | 4.6 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED BHERBHERI PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16140 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Bherbheri Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000904/2023-2024 | 2471/NMD-II | 11/08/2023 | 13/03/2025 | M/S CHANDRANATH MUKHERJEE | 18.58 | 0 | 0 | 60
Total | [13 empty] | 766.68 | 0 | 0