## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Providing House connection for GOPALPUR PWSS under Cooch Behar Division. PHE Dte PART Y | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000060/2022-2023 | 257/CD | 24/05/2022 | 23/06/2022 | MALAY KR.DEB | 9.68 | 9.68 | 100 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Construction of Street Stand Post at GOPALPUR Water Supply Scheme under Cooch Behar Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000183/2020-2021 | 1359/CD | 06/01/2021 | 20/02/2021 | SANKAR BANIK | 4.11 | 0 | 0 | 1
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 145/CD | 27/04/2023 |  | Resource Division | 121.15 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference under Cooch Behar Division, PHED. (Part-J) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000818/2022-2023 | 2010/CD W | 30/03/2023 | 06/04/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Hiring of Diesel Vehicle for inspection of site checking of FHTC and LDS, searching of land for different PWSS of Cooch Behar Division, PHE Dte. for 2 (Two) Months. (From June, 2023 to July, 2023) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000070/2023-2024 | 448/CD | 31/05/2023 | 30/07/2023 | RAJESH GUPTA | 0.34 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Hiring of Diesel Vehicle for inspection of site checking of FHTC and LDS, searching of land for different PWSS of Cooch Behar Sadar Sub-Division under Cooch Behar Division, PHE Dte. for 3 (Three) Months. (From May, 2023 to July, 2023). | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000069/2023-2024 | 126/CD | 26/04/2023 | 25/07/2023 | ANIMESH DHAR CHOUDHURY | 0.5 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-I Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000823/2022-2023 | 2001/CD | 29/03/2023 | 28/05/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 19
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Hiring of Diesel Vehicle for inspection of site checking of FHTC and LDS, searching of land for different PWSS of Cooch Behar Sadar Sub-Division under Cooch Behar Division, PHE Dte. for 3 (Three) Months. (From February, 2023 to April, 2023) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000831/2022-2023 | 1448/CDW | 06/01/2023 | 06/04/2023 | ANIMESH DHAR CHOUDHURY | 0.5 | 0 | 0 | 82
9 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | NEW SERVICE CONNECTION CHARGES AT GOPALPUR PWSS PH-II |  |  | BILL/02738/2023-2024 | BP-2023-24-613 | 16/02/2024 |  | WBSEDCL | 5.74 | 0 | 0 | null
10 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | NEW SERVICE CONNECTION CHARGES AT GOPALPUR PWSS PH-II |  |  | BILL/02738/2023-2024 | BP-2023-24-613 | 16/02/2024 |  | WBSEDCL | 5.74 | 0 | 0 | null
11 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | NEW SERVICE CONNECTION CHARGE AT GOPALPUR PWSS PH-I |  |  | BILL/02734/2023-2024 | BP-2023-24-612 | 16/02/2024 |  | WBSEDCL | 5.23 | 0 | 0 | null
12 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | NEW SERVICE CONNECTION CHARGE AT GOPALPUR PWSS PH-I |  |  | BILL/02734/2023-2024 | BP-2023-24-612 | 16/02/2024 |  | WBSEDCL | 5.23 | 0 | 0 | null
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Execution of different works related to AUG. of GOPALPUR PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1368/1-5/NBC-1; Dt.: 28-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000639/2022-2023 | 2016/CD | 30/03/2023 | 06/11/2023 | MATARA CONSTRUCTION CO. | 498.28 | 66.97 | 13.44 | 50
14 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Gopalpur Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000905/2023-2024 | 2470/NMD-II | 11/08/2023 | 10/09/2023 | M/S B ENTERPRISE | 21.79 | 2.81 | 12.88 | 15
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Name of Work: Execution of different works related to GOPALPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000257/2023-2024 | 1025/CD | 22/09/2023 | 21/11/2023 | ABHIJIT KUMAR DAS | 22 | 5.68 | 25.82 | 51
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Execution of different works related to KHOLTA PWSS under JAL JEEVAN MISSION P A |  |  | ORD/000073/2024-2025 | 4001 | 06/06/2024 | 04/09/2024 | M/S T R PARIK | 51.38 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Execution of different works related to BANESWAR PWSS under JAL JEEVAN MISSION |  |  | ORD/000088/2024-2025 | 1285/CD | 08/07/2024 | 06/10/2024 | MS DD ENTERPRISE | 9.26 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Execution of different works related to BARAIBARI PWSS under JAL JEEVAN MISSION |  |  | ORD/000087/2024-2025 | 1191/CD | 25/06/2024 | 23/09/2024 | ASHIM KUMAR CHAKRABORTY | 97.02 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 1539/CD | 16/08/2024 |  | Resource Division | 23.26 | 0 | 0 | 0
Total | [13 empty] | 20672.45 | 87.11 | 0.42