## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Construction of Street Stand Post at GOPALPUR Water Supply Scheme under Cooch Behar Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000183/2020-2021 | 1359/CD | 06/01/2021 | 20/02/2021 | SANKAR BANIK | 4.11 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference under Cooch Behar Division, PHED. (Part-J) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000818/2022-2023 | 2010/CD W | 30/03/2023 | 06/04/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-I Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000823/2022-2023 | 2001/CD | 29/03/2023 | 29/05/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 19
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Hiring of Diesel Vehicle for inspection of site checking of FHTC and LDS, searching of land for different PWSS of Cooch Behar Sadar Sub-Division under Cooch Behar Division, PHE Dte. for 3 (Three) Months. (From February, 2023 to April, 2023) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000831/2022-2023 | 1448/CDW | 06/01/2023 | 06/04/2023 | ANIMESH DHAR CHOUDHURY | 0.5 | 0 | 0 | 82
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Hiring of Diesel Vehicle for inspection of site checking of FHTC and LDS, searching of land for different PWSS of Cooch Behar Sadar Sub-Division under Cooch Behar Division, PHE Dte. for 3 (Three) Months. (From May, 2023 to July, 2023). | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000069/2023-2024 | 126/CD | 26/04/2023 | 26/07/2023 | ANIMESH DHAR CHOUDHURY | 0.5 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Providing House connection for GOPALPUR PWSS under Cooch Behar Division. PHE Dte PART Y | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000060/2022-2023 | 257/CD | 24/05/2022 | 23/06/2022 | MALAY KR.DEB | 9.68 | 9.68 | 100 | 1
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 145/CD | 27/04/2023 | 27/04/2023 | Resource Division | 121.15 | 0 | 0 | 0
8 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Gopalpur Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000905/2023-2024 | 2470/NMD-II | 11/08/2023 | 10/09/2023 | M/S B ENTERPRISE | 21.79 | 5.61 | 25.76 | 15
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Name of Work: Execution of different works related to GOPALPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000257/2023-2024 | 1025/CD | 22/09/2023 | 21/11/2023 | ABHIJIT KUMAR DAS | 22 | 11.36 | 51.63 | 51
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO GOPALPUR & Baraibari PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000574/2024-2025 | 2258/CD | 23/12/2024 | 21/02/2025 | ASHIM KUMAR CHAKRABORTY | 15.62 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 1539/CD | 16/08/2024 | 16/08/2024 | Resource Division | 23.26 | 0 | 0 | 0
12 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | NEW SERVICE CONNECTION CHARGES AT GOPALPUR PWSS PH-II |  |  | BILL/02738/2023-2024 | BP-2023-24-613 | 16/02/2024 | 16/02/2024 | WBSEDCL | 5.74 | 0 | 0 | 0
13 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | NEW SERVICE CONNECTION CHARGE AT GOPALPUR PWSS PH-I |  |  | BILL/02734/2023-2024 | BP-2023-24-612 | 16/02/2024 | 16/02/2024 | WBSEDCL | 5.23 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Execution of different works related to AUG. of GOPALPUR PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1368/1-5/NBC-1; Dt.: 28-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000639/2022-2023 | 2016/CD | 30/03/2023 | 22/01/2026 | MATARA CONSTRUCTION CO. | 498.28 | 273.2 | 54.83 | 50
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Hiring of Diesel Vehicle for inspection of site checking of FHTC and LDS, searching of land for different PWSS of Cooch Behar Division, PHE Dte. for 2 (Two) Months. (From June, 2023 to July, 2023) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000070/2023-2024 | 448/CD | 31/05/2023 | 31/07/2023 | RAJESH GUPTA | 0.34 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Hiring of Diesel Vehicle for inspection of site checking of FHTC and LDS, searching of land for different PWSS of Cooch Behar Sadar Sub-Division under Cooch Behar Division, PHE Dte. for 2 (TWO) Months. (From August, 2023 to September, 2023). | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000233/2023-2024 | 592/CD | 06/07/2023 | 06/09/2023 | RAJESH GUPTA | 0.34 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Hiring of Diesel Vehicle for inspection of site checking of FHTC and LDS, searching of land for different PWSS under H.Q. Cooch Behar Division by Junior Engineer, H.Q. Cooch Behar Division, PHE Dte. for 03 (Three) Months. (From Nov. 2023 to January, 2024). | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000432/2023-2024 | 1243/CD | 31/10/2023 | 31/01/2024 | RAJESH GUPTA | 0.5 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 157.49 | 0.8 | 20
19 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Execution of different works related to BARAIBARI PWSS under JAL JEEVAN MISSION | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000087/2024-2025 | 1191/CD | 25/06/2024 | 22/03/2025 | ASHIM KUMAR CHAKRABORTY | 97.02 | 0 | 0 | 80
20 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Execution of different works within KHOLTA area related to AUG. GOPALPUR PWSS under JAL JEEVAN MISSION P A | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000032/2024-2025 | 1141/CD | 14/06/2024 | 10/04/2025 | DIPANKAR BANIK | 51.38 | 0 | 0 | 50
21 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO SAJHERPAR KHATALBARI CHAKCHAKA ZONE II MARANADIRKUTHI & GOPALPUR PWSS UNDER JAL JEEVAN MISSION. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000533/2024-2025 | 2217/CD | 23/12/2024 | 20/08/2025 | MATARA CONSTRUCTION CO. | 80.28 | 0 | 0 | 80
22 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO GOPALPUR PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000583/2024-2025 | 2266/CD | 23/12/2024 | 21/08/2025 | MATARA CONSTRUCTION CO. | 57.15 | 0 | 0 | 40
23 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16146 | Augmentation | Execution of different works related (Within area of BANESWAR) to GOPALPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000088/2024-2025 | 1285/CD | 08/07/2024 | 01/04/2025 | MS DD ENTERPRISE | 9.26 | 2.07 | 22.4 | 98
Total | [13 empty] | 20815.38 | 461.38 | 2.22