## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED HEMKUMARI PIPED WATER SUPPLY SCHEME ZONE-I (PART-B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION, PHED. | SM/16147 | Augmentation | Providing FHTC & other allied works at HEMKUMARI ZONE I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000820/2022-2023 | 1858/CD | 14/03/2023 | 13/04/2023 | M/S. MANDAL CONSTRUCTION | 9.98 | 9.12 | 91.44 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED HEMKUMARI PIPED WATER SUPPLY SCHEME ZONE-I (PART-B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION, PHED. | SM/16147 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 204/CD | 27/04/2023 | 27/04/2023 | Resource Division | 18.27 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED HEMKUMARI PIPED WATER SUPPLY SCHEME ZONE-I (PART-B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION, PHED. | SM/16147 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED HEMKUMARI PIPED WATER SUPPLY SCHEME ZONE-I (PART-B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION, PHED. | SM/16147 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO HEMKUMARI ZONE-I HEMKUMARI ZONE-I (PB) HEMKUMARI ZONE-III & DEBOTTAR BAKSHIGANJ PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000569/2024-2025 | 2253/CD | 23/12/2024 | 24/06/2025 | DAS ENTERPRISE | 36.07 | 0 | 0 | 50
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED HEMKUMARI PIPED WATER SUPPLY SCHEME ZONE-I (PART-B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION, PHED. | SM/16147 | Augmentation | EXECUTION OF DIFFERENT WORKS (within HEMKUMARI area) RELATED TO GAJENDRAPUR CHOWRANGEE PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000661/2024-2025 | 90/CD | 17/01/2025 | 16/07/2025 | SHRI ANNAPURNA DISTRIBUTORS | 76.94 | 0 | 0 | 40
Total | [13 empty] | 19930.54 | 9.12 | 0.05