## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-I PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16149 | Augmentation | Laying of Delivery line , with DI pipe Line , Road & Bridge crossing , UPVC Pipe line with some other allied works related to Pipe line at MAHISKUCHI W.S.S under Tufanganj Sub ¿ Division, P.H.E Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000192/2020-2021 | 1363/CD | 06/01/2021 | 15/02/2021 | ASHIM KUMAR CHAKRABORTY | 4.92 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-I PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16149 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 214/CD | 27/04/2023 |  | Resource Division | 27.93 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-I PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16149 | Augmentation | Execution of different works related to AUG. of MAHISHKUCHI ZONE 1 PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 30/1-5/NBC-1; Dt.: 13-04-23 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000001/2023-2024 | 42/CD | 17/04/2023 | 14/09/2023 | RAJIB CHAKRABORTY | 252.31 | 74.17 | 29.4 | 59
4 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-I PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16149 | Augmentation | QUOTATION FOR NSC AT MAHISKUCHI TW NO I,Z-I |  |  | BILL/02465/2023-2024 | BP-2023-24-539 | 17/01/2024 |  | WBSEDCL | 7.93 | 0 | 0 | 0
5 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-I PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16149 | Augmentation | QUOTATION FOR NSC AT MAHISHKUCHI TW NO II,Z-I |  |  | BILL/02464/2023-2024 | BP-2023-24-538 | 17/01/2024 |  | WBSEDCL | 5.82 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-I PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16149 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mathabhanga-I Water Supply Scheme under Cooch Behar Division, PHED. |  | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000466/2023-2024 | 211/CD | 05/02/2024 | 05/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-I PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16149 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mathabhanga-II Water Supply Scheme under Cooch Behar Division, PHED. |  | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000467/2023-2024 | 212/CD | 05/02/2024 | 05/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-I PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16149 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mekhliganj Water Supply Scheme under Cooch Behar Division, PHED. |  | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000468/2023-2024 | 213/CD | 05/02/2024 | 05/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-I PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16149 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Haldibari Water Supply Scheme under Cooch Behar Division, PHED. |  | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000469/2023-2024 | 214/CD | 05/02/2024 | 05/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-I PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16149 | Augmentation | Execution of different works related to MAHISHKUCHI Z 1 PWSS under JAL JEEVAN MISSION |  |  | ORD/000591/2023-2024 | 630/CD | 11/03/2024 | 10/05/2024 | RAJIB CHAKRABORTY | 96.41 | 0 | 0 | 0
11 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-I PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16149 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Mahiskuchi Water Supply Scheme TW No.-I, II and III of Zone-I under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000919/2023-2024 | 2497/NMD-II | 14/08/2023 | 13/09/2023 | B.B CONCERNED | 31.62 | 0 | 0 | 30
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-I PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16149 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20220.17 | 78.11 | 0.39