## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED NAJIRGANJ PWSS DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16150 | Augmentation | Providing House connection for NAZIRGANJ PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000255/2022-2023 | 753/CD | 31/08/2022 | 15/10/2022 | SANKAR CHAKRABORTY | 9.92 | 9.85 | 99.38 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED NAJIRGANJ PWSS DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16150 | Augmentation | Providing FHTC Works, Laying of pipe line at NAZIRGANJ W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000544/2021-2022 | 1644/CD | 29/03/2022 | 28/05/2022 | SANKAR CHAKRABORTY | 29.95 | 29.95 | 100 | 1
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED NAJIRGANJ PWSS DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16150 | Augmentation | Providing FHTC & other allied works at NAJIRGANJ ZI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000365/2022-2023 | 1018/CD | 29/09/2022 | 29/10/2022 | SANKAR CHAKRABORTY | 9.97 | 9.97 | 100 | 1
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED NAJIRGANJ PWSS DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16150 | Augmentation | Execution of different works related to AUG of NAJIRGANJ PWSS under JAL JEEVAN MISSION. SE,NBC-1,PHED A.O. No.: 1375/1-5/NBC-1; Dt.: 28-02-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000695/2022-2023 | 2002/CD | 29/03/2023 | 14/09/2025 | M/S. NITYAGOPAL BANIK | 230.39 | 186.19 | 80.81 | 32
5 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED NAJIRGANJ PWSS DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16150 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Najirganj Water Supply Scheme TW No.- I under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000908/2023-2024 | 2469/NMD-II | 11/08/2023 | 10/09/2023 | MADHAB SAHA | 10.6 | 9.96 | 93.98 | 100
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED NAJIRGANJ PWSS DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16150 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 164/CD | 27/04/2023 | 27/04/2023 | Resource Division | 41.86 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED NAJIRGANJ PWSS DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16150 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED NAJIRGANJ PWSS DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16150 | Augmentation | HIRING VEHICLE |  |  | BILL/00480/2024-2025 | BP-212 | 31/07/2024 | 31/07/2024 | BHAGWATI BHUJEL | 0.66 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED NAJIRGANJ PWSS DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16150 | Augmentation | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING ALONGSIDE KHARUBHAJ KHOCHABARI ROAD ADJACENT NAJIRGANJ VR ( IN stretches UNDER PWD DINHATA SUB DIVISION UNDER PWD Cooch Behar division in the DISTRICT OF COOCHBEHAR |  |  | BILL/00357/2024-2025 | BP-305 | 31/08/2024 | 31/08/2024 | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 4.38 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED NAJIRGANJ PWSS DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16150 | Augmentation | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING ALONGSIDE KISMAT DASGRAM VR ADJACENT TO NAJIRGANJ ( IN stretches UNDER PWD DINHATA SUB DIVISION UNDER PWD Cooch Behar division in the DISTRICT OF COOCHBEHAR |  |  | BILL/00356/2024-2025 | BP-304 | 31/08/2024 | 31/08/2024 | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 18.53 | 0 | 0 | 0
11 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED NAJIRGANJ PWSS DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16150 | Augmentation | Charges for new service connection at Nazirganj pwss, P/H-III. |  |  | BILL/00208/2024-2025 | BP-43/24-25 | 29/04/2024 | 29/04/2024 | WBSEDCL | 4.05 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED NAJIRGANJ PWSS DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16150 | Augmentation | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING ALONGSIDE NAJIRHAT DIGHALTARY ADJACENT TO NAJIRGANJ VR ( IN stretches UNDER PWD DINHATA SUB DIVISION UNDER PWD Cooch Behar division in the DISTRICT OF COOCHBEHAR |  |  | BILL/00358/2024-2025 | 306 | 31/08/2024 | 31/08/2024 | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 4.88 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED NAJIRGANJ PWSS DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16150 | Augmentation | EXECUTION OF DIFFERENT WORKS (within NAJIRGANJ, BHANGRI PRATHAM KHANDA, RUIER KHUTHI & HARIBHANGA KHATTIMARI area) RELATED TO Bhulki PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000655/2024-2025 | 84/CD | 17/01/2025 | 13/11/2025 | BIJOY ROY | 84.6 | 0 | 0 | 40
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED NAJIRGANJ PWSS DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/16150 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000040/2025-2026 | 676/CD | 14/05/2025 | 07/08/2026 | M/S J C ENTERPRISE | 67.52 | 0 | 0 | 70
Total | [13 empty] | 20306.62 | 245.93 | 1.21