## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata - II | Coochbehar Division | Tanapakha Piped Water Supply Scheme | SM/16152 | New | Execution of different works related to TANAPAKHA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000352/2023-2024 | 1336/CD | 24/11/2023 | 23/01/2024 | ABHIJIT KUMAR DAS | 31.55 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata - II | Coochbehar Division | Tanapakha Piped Water Supply Scheme | SM/16152 | New | Execution of different works related to Andaran Fulbari area under Tanapakha PWSS under JAL JEEVAN MISSION Z1 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000779/2023-2024 | 660/CD | 11/03/2024 | 10/05/2024 | UTTAM SAHA | 3.15 | 0 | 0 | 100
3 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | Tanapakha Piped Water Supply Scheme | SM/16152 | New | Charges for new service connection at Tanapaka pwss, P/H-II |  |  | BILL/00274/2024-2025 | BP-73/24-25 | 16/05/2024 |  | WBSEDCL | 6.65 | 0 | 0 | null
4 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | Tanapakha Piped Water Supply Scheme | SM/16152 | New | Charges for new service connection at Tanapaka pwss, P/H-II |  |  | BILL/00274/2024-2025 | BP-73/24-25 | 16/05/2024 |  | WBSEDCL | 6.65 | 0 | 0 | null
5 | COOCHBEHAR | Dinhata - II | Coochbehar Division | Tanapakha Piped Water Supply Scheme | SM/16152 | New | Execution of different works related to AUG of TANAPAKHA PWSS under JAL JEEVAN MISSION. SE,NBC-1,PHED A.O. No.: 44/1-5/NBC-1; Dt.: 17-04-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000007/2023-2024 | 45/CD | 17/04/2023 | 14/09/2023 | ABHIJIT KUMAR DAS | 133.43 | 28.32 | 21.22 | 80
Total | [13 empty] | 181.45 | 28.32 | 15.61