## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-II | Coochbehar Division | Tanapakha Piped Water Supply Scheme | SM/16152 | New | Execution of different works related to AUG of TANAPAKHA PWSS under JAL JEEVAN MISSION. SE,NBC-1,PHED A.O. No.: 44/1-5/NBC-1; Dt.: 17-04-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000007/2023-2024 | 45/CD | 17/04/2023 | 14/09/2023 | ABHIJIT KUMAR DAS | 133.43 | 101.92 | 76.38 | 80
2 | COOCHBEHAR | Dinhata-II | Coochbehar Division | Tanapakha Piped Water Supply Scheme | SM/16152 | New | Execution of different works related to TANAPAKHA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000352/2023-2024 | 1336/CD | 24/11/2023 | 23/01/2024 | ABHIJIT KUMAR DAS | 31.55 | 13.51 | 42.82 | 55
3 | COOCHBEHAR | Dinhata-II | Coochbehar Division | Tanapakha Piped Water Supply Scheme | SM/16152 | New | Execution of different works related to Andaran Fulbari area under Tanapakha PWSS under JAL JEEVAN MISSION Z1 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000779/2023-2024 | 660/CD | 11/03/2024 | 10/05/2024 | UTTAM SAHA | 3.15 | 2.92 | 92.84 | 100
4 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | Tanapakha Piped Water Supply Scheme | SM/16152 | New | Charges for new service connection at Tanapaka pwss, P/H-II |  |  | BILL/00274/2024-2025 | BP-73/24-25 | 16/05/2024 | 16/05/2024 | WBSEDCL | 6.65 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-II | Coochbehar Division | Tanapakha Piped Water Supply Scheme | SM/16152 | New | HORDING/ SIGN BOARD FOR IEC CAMPAINING AT GP OFFICE / BLOCK OFFICE & DIFFERENT HEALTH CENTERS UNDER COOCH BEHAR DIVISION , PHE Dte | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000704/2024-2025 | 2326/CD | 23/12/2024 | 21/02/2025 | ISLAMPUR SWARNADEEP SOCIETY | 48.03 | 0 | 0 | 100
6 | COOCHBEHAR | Dinhata-II | Coochbehar Division | Tanapakha Piped Water Supply Scheme | SM/16152 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000051/2025-2026 | 722/CD | 17/05/2025 | 15/08/2025 | GOUTAM KUMAR DAS | 32.95 | 0 | 0 | 100
7 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | Tanapakha Piped Water Supply Scheme | SM/16152 | New | Charges for new service connection at Tanapaka PWSS, P/H-I in the dist of Coochbehar |  |  | BILL/02015/2024-2025 | BP-472/24-25 | 17/03/2025 | 17/03/2025 | WBSEDCL | 8.68 | 0 | 0 | 0
Total | [13 empty] | 264.45 | 118.35 | 44.75