## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | AUGUMENTATION OF GROUND WATER BASED MARANADIRKUTHI PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16153 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Maranadirkuthi Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,,Apd. |  |  | ORD/001079/2023-2024 | 2776/NMD-II | 05/10/2023 | 04/11/2023 | BONANZA ENTERPRISE | 10.54 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED MARANADIRKUTHI PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16153 | Augmentation | Name of Work: Execution of different works related to MARANADIR KUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000270/2023-2024 | 1038/CD | 22/09/2023 | 21/11/2023 | COOCH BEHAR U/E CO-OP-LAB. CONT. & CONSTN. SO-LTD | 12.6 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED MARANADIRKUTHI PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16153 | Augmentation | Execution of different works related to AUG. of MARANADIRKUTHI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1376/1-5/NBC-1; Dt.: 28-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000646/2022-2023 | 2017/CD | 30/03/2023 | 27/08/2023 | BISWAJIT GUHA | 131.29 | 122.87 | 93.59 | 67
4 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED MARANADIRKUTHI PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16153 | Augmentation | Execution of different works related to KHAGRABARI Z PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000065/2024-2025 | 1272/CD | 03/07/2024 | 01/10/2024 | BILTU DAS | 84.91 | 0 | 0 | 70
5 | COOCHBEHAR |  | Northern Mechanical Division II | AUGUMENTATION OF GROUND WATER BASED MARANADIRKUTHI PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16153 | Augmentation | NEW SERVICE CONNECTION AT MARANADIRKUTHI PWSS, PH-III |  |  | BILL/02890/2023-2024 | BP-2023-24-661 | 04/03/2024 | 04/03/2024 | WBSEDCL | 8.35 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED MARANADIRKUTHI PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16153 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
7 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED MARANADIRKUTHI PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16153 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO SAJHERPAR KHATALBARI CHAKCHAKA ZONE II MARANADIRKUTHI & GOPALPUR PWSS UNDER JAL JEEVAN MISSION. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000533/2024-2025 | 2217/CD | 23/12/2024 | 20/08/2025 | MATARA CONSTRUCTION CO. | 80.28 | 0 | 0 | 80
8 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED MARANADIRKUTHI PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16153 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000096/2025-2026 | 748/CD | 17/05/2025 | 15/08/2025 | GOUTAM KUMAR DAS | 35.19 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED MARANADIRKUTHI PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16153 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000331/2025-2026 | 786/CD | 23/05/2025 | 20/09/2025 | M/S. MANDAL CONSTRUCTION | 9.56 | 0 | 0 | 30
10 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED MARANADIRKUTHI PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16153 | Augmentation | Execution of different works related (Within Area of KHAGRABARI) to MARANADIRKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000085/2024-2025 | 1311/CD | 16/07/2024 | 14/10/2024 | DAS ENTERPRISE | 1.32 | 0.24 | 17.92 | 94
Total | [13 empty] | 20163.32 | 123.11 | 0.61