## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Tufanganj-I | Coochbehar Division | BAJEJAMA CHILAKHANA PRATHAM KHANDA PWSS | SM/16154 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
2 | COOCHBEHAR | Tufanganj-I | Northern Mechanical Division II | BAJEJAMA CHILAKHANA PRATHAM KHANDA PWSS | SM/16154 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bajejama Chilakhana Pratham Khanada PWSS, TW no I & II in the district of Coochbehar under Northern Mechanical Division-II, PHE Dte. |  |  | ORD/000353/2024-2025 | 2420/NMD-II | 25/10/2024 | 24/11/2024 | M/S A.D. ENTERPRISE | 22.34 | 0 | 0 | 0
3 | COOCHBEHAR | Tufanganj-I | Coochbehar Division | BAJEJAMA CHILAKHANA PRATHAM KHANDA PWSS | SM/16154 | New | Execution of different works related to Chilakhana PWSS under JAL JEEVAN MISSION |  |  | ORD/000778/2023-2024 | 658/CD | 11/03/2024 | 10/05/2024 | GOUTAM KUMAR DAS | 4.62 | 0 | 0 | 0
4 | COOCHBEHAR | Tufanganj-I | Coochbehar Division | BAJEJAMA CHILAKHANA PRATHAM KHANDA PWSS | SM/16154 | New | Execution of different works related to TFG LAB under BAJEJAMA CHILAKHANA PRATHAM KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000781/2023-2024 | 662/CD | 11/03/2024 | 10/05/2024 | BHAGWATI BHUJEL | 6.94 | 6.94 | 100 | 100
5 | COOCHBEHAR | Tufanganj-I | Coochbehar Division | BAJEJAMA CHILAKHANA PRATHAM KHANDA PWSS | SM/16154 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000030/2025-2026 | 718/CD | 17/05/2025 | 10/08/2026 | UTPAL CHAKRABORTY | 32.03 | 0 | 0 | 80
6 | COOCHBEHAR | Tufanganj-I | Coochbehar Division | BAJEJAMA CHILAKHANA PRATHAM KHANDA PWSS | SM/16154 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000022/2025-2026 | 710/CD | 17/05/2025 | 13/11/2025 | UTTAM SAHA | 33.95 | 0 | 0 | 100
7 | COOCHBEHAR | Tufanganj-I | Coochbehar Division | BAJEJAMA CHILAKHANA PRATHAM KHANDA PWSS | SM/16154 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000027/2025-2026 | 715/CD | 17/05/2025 | 15/08/2025 | UTPAL CHAKRABORTY | 22.76 | 0 | 0 | 0
8 | COOCHBEHAR | Tufanganj-I | Coochbehar Division | BAJEJAMA CHILAKHANA PRATHAM KHANDA PWSS | SM/16154 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000095/2025-2026 | 736/CD | 17/05/2025 | 13/11/2025 | AASHIRBAD ENTERPRISE | 42.14 | 0 | 0 | 85
Total | [13 empty] | 19954.05 | 6.94 | 0.03