## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Tufanganj-I | Coochbehar Division | JAIGIR CHILAKHANA Piped Water Supply Scheme | SM/16155 | New | Material Requisition To Resource Division |  |  | RTOR000122/2023-2024 | 230/CD | 27/04/2023 | 27/04/2023 | Resource Division | 24.7 | 0 | 0 | 0
2 | COOCHBEHAR | Tufanganj-I | Northern Mechanical Division II | JAIGIR CHILAKHANA Piped Water Supply Scheme | SM/16155 | New | QUOTATION FOR NSC AT JAIGIR CHILAKHANA PH NO II |  |  | BILL/01055/2023-2024 | BP-2023-24-255 | 02/08/2023 | 02/08/2023 | WBSEDCL | 5.44 | 0 | 0 | 0
3 | COOCHBEHAR | Tufanganj-I | Northern Mechanical Division II | JAIGIR CHILAKHANA Piped Water Supply Scheme | SM/16155 | New | QUOTATION FOR NSC AT JAIGIR CHILAKHANA PH NO I |  |  | BILL/01054/2023-2024 | BP-2023-24-265 | 02/08/2023 | 02/08/2023 | WBSEDCL | 4.87 | 0 | 0 | 0
4 | COOCHBEHAR | Tufanganj-I | Coochbehar Division | JAIGIR CHILAKHANA Piped Water Supply Scheme | SM/16155 | New | Execution of different works related to JAIGIR CHILAKHANA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000579/2023-2024 | 619/CD | 11/03/2024 | 10/05/2024 | GHOSH AND SAHA CONSTRUCTION | 82 | 0 | 0 | 10
5 | COOCHBEHAR | Tufanganj-I | Coochbehar Division | JAIGIR CHILAKHANA Piped Water Supply Scheme | SM/16155 | New | Material Requisition To Resource Division |  |  | RTOR000169/2023-2024 | 17/CD | 05/01/2024 | 05/01/2024 | Resource Division | 20.16 | 0 | 0 | 0
6 | COOCHBEHAR | Tufanganj-I | Coochbehar Division | JAIGIR CHILAKHANA Piped Water Supply Scheme | SM/16155 | New | SINKING TUBE WELL AT MARICHBARI PWSS |  |  | BILL/01452/2023-2024 | BP-925 | 29/01/2024 | 29/01/2024 | LONGLAST PIPES (INDIA) PVT. LTD. | 0.09 | 0 | 0 | 0
7 | COOCHBEHAR | Tufanganj-I | Coochbehar Division | JAIGIR CHILAKHANA Piped Water Supply Scheme | SM/16155 | New | execution of different works at falimari zone -I pwss |  |  | BILL/01514/2023-2024 | BP-953 | 31/01/2024 | 31/01/2024 | HARIDAS GHOSH | 80 | 0 | 0 | 0
8 | COOCHBEHAR | Tufanganj-I | Coochbehar Division | JAIGIR CHILAKHANA Piped Water Supply Scheme | SM/16155 | New | sinking tube-well at marichbari pwss |  |  | BILL/01515/2023-2024 | BP-902 | 15/01/2024 | 15/01/2024 | LONGLAST PIPES (INDIA) PVT. LTD. | 10.49 | 0 | 0 | 0
9 | COOCHBEHAR | Tufanganj-I | Coochbehar Division | JAIGIR CHILAKHANA Piped Water Supply Scheme | SM/16155 | New | EXCUTION OF DIFFERENT WORK AT LANKABAR PWSS |  |  | BILL/01462/2023-2024 | BP-962-P2 | 31/01/2024 | 31/01/2024 | NABIN DEBNATH | 0.1 | 0 | 0 | 0
10 | COOCHBEHAR | Tufanganj-I | Northern Mechanical Division II | JAIGIR CHILAKHANA Piped Water Supply Scheme | SM/16155 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Jagir Chilakhana Water Supply Scheme TW No.- I and II under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000697/2023-2024 | 2196/NMD-II | 28/07/2023 | 26/06/2025 | DIAMOND ELECTRICAL WORKS | 21.78 | 0 | 0 | 75
11 | COOCHBEHAR | Tufanganj-I | Coochbehar Division | JAIGIR CHILAKHANA Piped Water Supply Scheme | SM/16155 | New | Execution of different works related to AUG. of JAIGIR CHILAKHANA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000104/2023-2024 | 718/CD | 25/07/2023 | 13/08/2025 | GHOSH AND SAHA CONSTRUCTION | 603.14 | 0 | 0 | 5
Total | [13 empty] | 852.77 | 0 | 0