## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BILSI PIPED WATER SUPPLY SCHEME | SM/16156 | Augmentation | Construction of Pillar & other allied works for supporting of DI Pipeline at BILSI PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000225/2021-2022 | 758/CD | 03/12/2021 | 03/03/2022 | NABIN DEBNATH | 8.76 | 4.61 | 52.66 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BILSI PIPED WATER SUPPLY SCHEME | SM/16156 | Augmentation | Execution of different works related to BILSI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000418/2023-2024 | 1473/CD | 20/12/2023 | 12/02/2025 | UTPAL CHAKRABORTY | 83.84 | 75.81 | 90.42 | 20
3 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BILSI PIPED WATER SUPPLY SCHEME | SM/16156 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AGUMENTATION OF BILSI PWSS TW No.-I under NMD-II,PHE.Dte,Alipurduar. |  |  | ORD/000928/2023-2024 | 2525/NMD-II | 16/08/2023 | 15/09/2023 | M/S ABHISEK ENGINEERING CONCERN | 11.01 | 0 | 0 | 0
Total | [13 empty] | 103.61 | 80.42 | 77.62