## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BILSI PIPED WATER SUPPLY SCHEME | SM/16156 | Augmentation | Construction of Pillar & other allied works for supporting of DI Pipeline at BILSI PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000225/2021-2022 | 758/CD | 03/12/2021 | 03/03/2022 | NABIN DEBNATH | 8.76 | 4.61 | 52.66 | 1
2 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BILSI PIPED WATER SUPPLY SCHEME | SM/16156 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AGUMENTATION OF BILSI PWSS TW No.-I under NMD-II,PHE.Dte,Alipurduar. |  |  | ORD/000928/2023-2024 | 2525/NMD-II | 16/08/2023 | 15/09/2023 | M/S ABHISEK ENGINEERING CONCERN | 11.01 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BILSI PIPED WATER SUPPLY SCHEME | SM/16156 | Augmentation | Execution of different works related to BILSI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000418/2023-2024 | 1473/CD | 20/12/2023 | 12/02/2025 | UTPAL CHAKRABORTY | 83.84 | 75.81 | 90.42 | 20
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BILSI PIPED WATER SUPPLY SCHEME | SM/16156 | Augmentation | FABRICATION AND INSTALLATION OF LAND POSSESSION SIGN BOARD AT EVERY LANDS OF DIFFERENT PWSS WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, PHE Dte. UNDER JJM (PART-C) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000623/2024-2025 | 2325/CD | 23/12/2024 | 21/02/2025 | ISLAMPUR SWARNADEEP SOCIETY | 44.29 | 0 | 0 | 100
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BILSI PIPED WATER SUPPLY SCHEME | SM/16156 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000025/2025-2026 | 713/CD | 17/05/2025 | 15/08/2025 | UTPAL CHAKRABORTY | 18.29 | 0 | 0 | 100
6 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BILSI PIPED WATER SUPPLY SCHEME | SM/16156 | Augmentation | Charges for new service connection at Aug of Bilsi PWSS, P/H-III under Coochbehar dist. |  |  | BILL/00436/2025-2026 |  | 20/05/2025 | 20/05/2025 | WBSEDCL | 9.78 | 0 | 0 | 0
Total | [13 empty] | 175.97 | 80.42 | 45.7