## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B | SM/16164 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B, TW No.-I and II under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Cooch-Behar Mechanical Sub-Division, | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000931/2023-2024 | 2527/NMD-II | 16/08/2023 | 15/09/2023 | M/S KUNDU CONSTRUCTION | 21.08 | 0 | 0 | 40
2 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B | SM/16164 | New | Material Requisition To Resource Division |  |  | RTOR000192/2023-2024 | 87/CD | 11/01/2024 | 11/01/2024 | Resource Division | 13.35 | 0 | 0 | 0
3 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B | SM/16164 | New | Execution of different works related to Aug. of PHULBARI PART-B PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 34/1-5/NBC-1; Dt.: 13-04-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000005/2023-2024 | 41/CD | 13/04/2023 | 29/09/2025 | SHREE RANI SATI ENTERPRISE | 486.26 | 0 | 0 | 44
4 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B | SM/16164 | New | Execution of different works related to PHULBARI PART-B PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000024/2024-2025 | 1132/CD | 14/06/2024 | 09/02/2025 | SHREE RANI SATI ENTERPRISE | 97.07 | 0 | 0 | 55
5 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B | SM/16164 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
6 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B | SM/16164 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B | SM/16164 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000112/2025-2026 | 731/CD | 17/05/2025 | 15/08/2025 | KAJAL KUMAR DE | 7.22 | 0 | 0 | 30
8 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B | SM/16164 | New | Yard lighting arrangement at Head Work Site for Different PWSS (BALASUNDAR and others) under JJM in the BLOCK: Mathabhanga-II, DISTRICT: Coochbehar under NMD-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000168/2025-2026 | 1387/NMD-II | 26/06/2025 | 26/07/2025 | A.K SIKDAR | 18.14 | 0 | 0 | 0
9 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B | SM/16164 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000074/2025-2026 | 789/CD | 23/05/2025 | 21/08/2025 | SHREE RANI SATI ENTERPRISE | 69.41 | 0 | 0 | 0
10 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B | SM/16164 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000075/2025-2026 | 752/CD | 17/05/2025 | 15/08/2025 | SHREE RANI SATI ENTERPRISE | 56.67 | 0 | 0 | 0
11 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B | SM/16164 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000254/2025-2026 | 761/CD | 17/05/2025 | 15/08/2025 | AKANSHA COMMERCIAL PVT. LTD. | 67.3 | 0 | 0 | 0
Total | [13 empty] | 21113.85 | 0 | 0