## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B | SM/16164 | New | Material Requisition To Resource Division |  |  | RTOR000192/2023-2024 | 87/CD | 11/01/2024 |  | Resource Division | 13.35 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B | SM/16164 | New | Execution of different works related to Aug. of PHULBARI PART-B PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 34/1-5/NBC-1; Dt.: 13-04-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000005/2023-2024 | 41/CD | 13/04/2023 | 10/09/2023 | SHREE RANI SATI ENTERPRISE | 486.26 | 89.38 | 18.38 | 44
3 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B | SM/16164 | New | Execution of different works related to FULBARI PART B PWSS under JAL JEEVAN MISSION |  |  | ORD/000024/2024-2025 | 1132/CD | 14/06/2024 | 13/08/2024 | SHREE RANI SATI ENTERPRISE | 97.07 | 0 | 0 | 0
4 | COOCHBEHAR | Mathabhanga - II | Northern Mechanical Division II | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B | SM/16164 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B, TW No.-I and II under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Cooch-Behar Mechanical Sub-Division, | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000931/2023-2024 | 2527/NMD-II | 16/08/2023 | 15/09/2023 | M/S KUNDU CONSTRUCTION | 21.08 | 0 | 0 | 40
5 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B | SM/16164 | New | Execution of different works related to FULBARI PART A PWSS under JAL JEEVAN MISSION |  |  | ORD/000077/2024-2025 | 4005 | 18/06/2024 | 16/09/2024 | SHREE RANI SATI ENTERPRISE | 37.3 | 0 | 0 | 0
6 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B | SM/16164 | New | Execution of different works related to FULBARI PART B PWSS under JAL JEEVAN MISSION |  |  | ORD/000081/2024-2025 | 4009 | 18/06/2024 | 16/09/2024 | SHREE RANI SATI ENTERPRISE | 0 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF PHULBARI PART-B | SM/16164 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20444.35 | 89.38 | 0.44