## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED DHALDIBARI PIPED WATER SUPPLY SCHEME OF TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16165 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000112/2023-2024 | 224/CD | 27/04/2023 | 27/04/2023 | Resource Division | 24.67 | 0 | 0 | 0
2 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED DHALDIBARI PIPED WATER SUPPLY SCHEME OF TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16165 | Augmentation | QUOTATION FOR NSC AT DHALDABRI PH NO-II |  |  | BILL/02206/2023-2024 | BP-2023-24-465 | 07/12/2023 | 07/12/2023 | WBSEDCL | 5.25 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED DHALDIBARI PIPED WATER SUPPLY SCHEME OF TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16165 | Augmentation | Execution of different works related to Aug. of DHALDIBARI PWSS under JAL SE,NBC-1,PHED A.O. No.: 1121/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000675/2022-2023 | 1992/CD | 28/03/2023 | 25/08/2023 | GOUTAM KUMAR DAS | 311.26 | 0 | 0 | 70
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED DHALDIBARI PIPED WATER SUPPLY SCHEME OF TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16165 | Augmentation | Execution of different works related to DHALDABRI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000551/2023-2024 | 620/CD | 11/03/2024 | 10/05/2024 | GOUTAM KUMAR DAS | 95.25 | 0 | 0 | 70
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED DHALDIBARI PIPED WATER SUPPLY SCHEME OF TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16165 | Augmentation | Charges for new service connection at Dhaldibari PWSS, P/H-II in the dist of Coochbehar. |  |  | BILL/00316/2024-2025 |  | 23/07/2024 | 23/07/2024 | WBSEDCL | 11.84 | 0 | 0 | 0
6 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED DHALDIBARI PIPED WATER SUPPLY SCHEME OF TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16165 | Augmentation | QUOTATION FOR NSC AT DHALDABRI TW NO II |  |  | BILL/02461/2023-2024 |  | 16/01/2024 | 16/01/2024 | WBSEDCL | 11.84 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED DHALDIBARI PIPED WATER SUPPLY SCHEME OF TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16165 | Augmentation | SINKING OF T/WELL AT DEOCHARAI PWSS |  |  | BILL/01387/2023-2024 | BP-798 | 08/12/2023 | 08/12/2023 | AUXILIARY TUBEWELL DRILLERS | 4.58 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED DHALDIBARI PIPED WATER SUPPLY SCHEME OF TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16165 | Augmentation | FHTC AT RASIKBILL PWSS |  |  | BILL/01281/2023-2024 | BP-810-P2 | 22/12/2023 | 22/12/2023 | GHOSH AND SAHA CONSTRUCTION | 1.21 | 0 | 0 | 0
9 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED DHALDIBARI PIPED WATER SUPPLY SCHEME OF TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16165 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGMENTATION OF GROUND WATER BASED DHALDIBARI PIPED WATER SUPPLY SCHEME OF TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT, TW No.- I and II under NMDII, PHE.Dte,Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000749/2023-2024 | 2199/NMD-II | 28/07/2023 | 27/08/2023 | NUPUR CHANDRA HALDER | 21.32 | 0 | 0 | 60
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED DHALDIBARI PIPED WATER SUPPLY SCHEME OF TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16165 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
Total | [13 empty] | 20276.51 | 0 | 0