## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-II PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16166 | Augmentation | Execution of different works related to Aug. of MAHISHKUCHI ZONE-II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000046/2023-2024 | 408/CD | 23/05/2023 | 18/09/2026 | UTPAL CHAKRABORTY | 214.33 | 111.31 | 51.94 | 60
2 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-II PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16166 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGMENTATION OF GROUND WATER BASED MAHISKUCHI ZONE-II PWSS TUFANGANJ II BLOCK WITHIN COOCHBEHAR DISTRICT, TW No.-I AND II under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000941/2023-2024 | 2546/NMD-II | 16/08/2023 | 01/07/2025 | SOUMEN ELECTRIC | 21.95 | 17.83 | 81.23 | 100
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-II PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16166 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-II PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16166 | Augmentation | Execution of different works (Within area of TATERKUITHI PWSS) related to MAHISHKUCHI ZONE-II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000078/2024-2025 | 1187/CD | 18/06/2024 | 11/09/2025 | SAIMONS CO- OPARATIVE LAB CONT & CONSTN SOCY LTD | 44.68 | 0 | 0 | 30
5 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-II PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16166 | Augmentation | Charges for new service connection at Mahiskuchi PWSS, (Zone-II) P/H-I. |  |  | BILL/01655/2024-2025 | BP-410/24-25 | 20/11/2024 | 20/11/2024 | WBSEDCL | 4.09 | 0 | 0 | 0
6 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-II PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16166 | Augmentation | Charges for new service connection at Mahiskuchi PWSS, (Zone-II) P/H-II |  |  | BILL/01654/2024-2025 | BP-409/24-25 | 20/11/2024 | 20/11/2024 | WBSEDCL | 4.58 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-II PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16166 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000027/2025-2026 | 715/CD | 17/05/2025 | 15/08/2025 | UTPAL CHAKRABORTY | 22.76 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-II PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16166 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000292/2025-2026 | 1422/CD | 11/08/2025 | 09/12/2025 | M/S SURAJIT MAJUMDER | 29.52 | 0 | 0 | 50
Total | [13 empty] | 20131.19 | 129.15 | 0.64