## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation OF AMBARI PIPED WATER SUPPLY SCHEME | SM/16350 | Augmentation | Preparation of DPR for Augmentation of Ambari Piped Water Supply Scheme under Cooch Behar Sadar Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000299/2021-2022 | 1014/CD/W | 10/01/2022 | 30/01/2022 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 3.24 | 3.24 | 100 | 100
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation OF AMBARI PIPED WATER SUPPLY SCHEME | SM/16350 | Augmentation | Providing 150nos. F.H.T.C. Connection in the command area at Ambari W.S.S. under Cooch Behar Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000098/2022-2023 | 70/SD | 13/05/2022 | 12/06/2022 | BISWAJIT GUHA | 4.86 | 4.86 | 100 | 1
3 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation OF AMBARI PIPED WATER SUPPLY SCHEME | SM/16350 | Augmentation | QUOTATION FOR NSC ATAMBARI AUG PH NO -II |  |  | BILL/01820/2023-2024 | BP-2023-24-378 | 27/09/2023 | 27/09/2023 | WBSEDCL | 7.97 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation OF AMBARI PIPED WATER SUPPLY SCHEME | SM/16350 | Augmentation | New service connection for AMBARI(AUG) PWSS, PH-I |  |  | BILL/02060/2023-2024 | BP-2023-24-430 | 05/12/2023 | 05/12/2023 | WBSEDCL | 7.3 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation OF AMBARI PIPED WATER SUPPLY SCHEME | SM/16350 | Augmentation | Execution of different works related to AMBARI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1341/1-5/NBC-1; Dt.: 24-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000599/2022-2023 | 1968/CD | 24/03/2023 | 21/08/2023 | ASHIM KUMAR CHAKRABORTY | 443.25 | 382.5 | 86.3 | 43
6 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation OF AMBARI PIPED WATER SUPPLY SCHEME | SM/16350 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Rejuvination of Ambari T.W No I of Zone-I under NMD-II,PHE.Dte,APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001138/2023-2024 | 2884/NMD-II | 17/10/2023 | 16/11/2023 | ASHWIRBAD WOOD CRAFT | 10.56 | 9.91 | 93.89 | 85
7 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation OF AMBARI PIPED WATER SUPPLY SCHEME | SM/16350 | Augmentation | Quotation for nsc at baneswar z-ii tw no-ii |  |  | BILL/02401/2023-2024 | BP-2023-24-552 | 18/01/2024 | 18/01/2024 | WBSEDCL | 10.47 | 0 | 0 | 0
8 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation OF AMBARI PIPED WATER SUPPLY SCHEME | SM/16350 | Augmentation | QUOTATION FOR NSC AT AMBARI TW NO II,Z-II |  |  | BILL/02449/2023-2024 |  | 08/01/2024 | 08/01/2024 | WBSEDCL | 10.47 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation OF AMBARI PIPED WATER SUPPLY SCHEME | SM/16350 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 191.91 | 0.97 | 20
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation OF AMBARI PIPED WATER SUPPLY SCHEME | SM/16350 | Augmentation | Execution of different works related to ICHAMARI & AMBARI PWSS under JAL JEEVAN MISSION P B | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000072/2024-2025 | 1185/CD | 18/06/2024 | 16/09/2024 | ASHIM KUMAR CHAKRABORTY | 38.89 | 0 | 0 | 75
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation OF AMBARI PIPED WATER SUPPLY SCHEME | SM/16350 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION |  |  | ORD/000050/2025-2026 | 705/CD | 17/05/2025 | 15/08/2025 | MS SSB CONSTRUCTION CO | 32.51 | 0 | 0 | 0
Total | [13 empty] | 20358.81 | 592.43 | 2.91