## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/16472 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO KRISHNAPUR PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000518/2024-2025 | 2295/CD | 23/12/2024 | 21/02/2025 | ARUN KUMAR KARMAKAR | 18.78 | 0 | 0 | 0
2 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/16472 | Augmentation | New service connection charge at Krishnapur pwss, P/H-III in the dist of Coochbehar |  |  | BILL/00681/2024-2025 | BP-177/24-25 | 03/07/2024 | 03/07/2024 | WBSEDCL | 22.54 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/16472 | Augmentation | Execution of different works related to Aug. of Krishnapur PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000119/2023-2024 | 635/CD | 12/07/2023 | 28/12/2025 | MS N S CONSTRUCTION | 153.55 | 0 | 0 | 100
4 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/16472 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Krishnapur Water Supply Scheme TW No.I under NMD-II,PHE.Dte,Apd. |  |  | ORD/000915/2023-2024 | 2494/NMD-II | 14/08/2023 | 13/09/2023 | SUDIP DUTTA | 10.89 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/16472 | Augmentation | Hiring of Diesel Vehicle for RWS COB Assistant Engineer for inspection of site checking of FHTC and LDS, searching of land for different PWSS under Cooch Behar Division, PHE Dte. (From 01-07-24 to 30-06-2025). | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000469/2024-2025 | 1241/CD | 29/06/2024 | 29/06/2025 | NARAYAN CHANDRA SARKAR | 1.92 | 0 | 0 | 100
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/16472 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO KRISHNAPUR & MANSAI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000548/2024-2025 | 2233/CD | 23/12/2024 | 21/02/2025 | GOUTAM KUMAR DAS | 63.55 | 0 | 0 | 40
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/16472 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000058/2025-2026 | 897/CD | 13/06/2025 | 11/09/2025 | M/S MM CONSTRUCTION | 9.05 | 0 | 0 | 0
Total | [13 empty] | 280.27 | 0 | 0