## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED MUKUL DANGA PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16473 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Mukuldanga Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. |  |  | ORD/000920/2023-2024 | 2498/NMD-II | 14/08/2023 | 13/09/2023 | MADHAB SAHA | 18.43 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MUKUL DANGA PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16473 | Augmentation | Execution of different works related to MUKULDANGA PWSS under JAL JEEVAN MISSION |  |  | ORD/000069/2024-2025 | 1321/CD | 19/07/2024 | 17/10/2024 | GOUTAM KUMAR DAS | 97 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MUKUL DANGA PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16473 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO MUKUL DANGA PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000559/2024-2025 | 2244/CD | 23/12/2024 | 21/02/2025 | SHREE RANI SATI ENTERPRISE | 41.8 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED MUKUL DANGA PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16473 | Augmentation | ELECTRIC QUOTATION FOR NEW SERVICE CONNECTION AT MUKULDANGA PWSS TW I. |  |  | BILL/01898/2024-2025 | BP-435/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 7.97 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MUKUL DANGA PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16473 | Augmentation | Execution of different works related to Aug. of MUKUL DANGA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1377/1-5/NBC-1; Dt.: 28-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000655/2022-2023 | 1999/CD | 28/03/2023 | 01/04/2025 | SHREE RANI SATI ENTERPRISE | 388.87 | 187.99 | 48.34 | 10
Total | [13 empty] | 554.06 | 187.99 | 33.93