## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED KONACHATRA ZONE-II PIPED WATER SUPPLY SCHEME OF SITAI BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16515 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Konachatra Water Supply Scheme TW No.-I and II of Zone-II under NMD-II,PHE.Dte,Apd. |  |  | ORD/001070/2023-2024 | 2738/NMD-II | 26/09/2023 | 26/10/2023 | A.S. ENTERPRISE | 21.07 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KONACHATRA ZONE-II PIPED WATER SUPPLY SCHEME OF SITAI BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16515 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 133/CD | 27/04/2023 | 27/04/2023 | Resource Division | 12.82 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KONACHATRA ZONE-II PIPED WATER SUPPLY SCHEME OF SITAI BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16515 | Augmentation | Execution of different works related to AUG. OF KONACHATRA ZONE-II PWSS under JAL JEEVAN MISSION | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000109/2023-2024 | 662/CD | 14/07/2023 | 11/12/2023 | SUMI ENTERPRISE | 327.88 | 61.58 | 18.78 | 18
4 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED KONACHATRA ZONE-II PIPED WATER SUPPLY SCHEME OF SITAI BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16515 | Augmentation | BILL FOR NEW SERVICE CONNECTION AT KONACHATRA PWSS ZONE-II PH I. |  |  | BILL/01403/2024-2025 | BP-401/24-25 | 29/10/2024 | 29/10/2024 | WBSEDCL | 17.19 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KONACHATRA ZONE-II PIPED WATER SUPPLY SCHEME OF SITAI BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16515 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KONACHATRA ZONE-II PIPED WATER SUPPLY SCHEME OF SITAI BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16515 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO KONACHATRA ZONE-II & BIJLICHATKA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000538/2024-2025 | 2222/CD | 23/12/2024 | 18/12/2025 | GEETA CONSTRUCTION | 54.42 | 0 | 0 | 75
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KONACHATRA ZONE-II PIPED WATER SUPPLY SCHEME OF SITAI BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16515 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS under JAL JEEVAN MISSION |  |  | ORD/000016/2025-2026 | 701/CD | 17/05/2025 | 15/08/2025 | UMEX POLYMERS PVT LTD | 39.89 | 0 | 0 | 0
Total | [13 empty] | 20262.56 | 61.58 | 0.3