## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AGUMENTATION OF BASRAJA PRATHAM KHANDA PWSS | SM/16516 | Augmentation | Execution of different works related to Aug. of Basraja Pratham Khanda PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000136/2023-2024 | 804/CD | 08/08/2023 | 30/03/2025 | AMBITIOUS ENTERPRISE | 336.6 | 0 | 0 | 60
2 | COOCHBEHAR |  | Northern Mechanical Division II | AGUMENTATION OF BASRAJA PRATHAM KHANDA PWSS | SM/16516 | Augmentation | Charges for new service connection at Aug of Bashraja pratham khanda PWSS, P/H-III in the dist of Coochbehar. |  |  | BILL/00979/2024-2025 | BP-291/24-25 | 22/08/2024 | 22/08/2024 | WBSEDCL | 6.18 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AGUMENTATION OF BASRAJA PRATHAM KHANDA PWSS | SM/16516 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
4 | COOCHBEHAR |  | Northern Mechanical Division II | AGUMENTATION OF BASRAJA PRATHAM KHANDA PWSS | SM/16516 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AGUMENTATION OF BASRAJA PRATHAM KHANDA PWSS TW No.-I under NMD-II,PHE.Dte,Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/002507/2023-2024 | 2539/NMD-II | 16/08/2023 | 15/09/2023 | KAMAKHYA ENTERPRISE | 11.03 | 0 | 0 | 80
5 | COOCHBEHAR |  | Coochbehar Division | AGUMENTATION OF BASRAJA PRATHAM KHANDA PWSS | SM/16516 | Augmentation | Hiring of Diesel Vehicle for inspection of site checking of FHTC and LDS, searching of land for different PWSS of Mathabhanga Sub-Division by Junior Engineer, Mathabhanga Sub-Division under Cooch Behar Division, PHE Dte. for 05 (Five) Months. (From February 2024 to June, 2024). | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000445/2023-2024 | 178,7/CD | 31/01/2024 | 30/06/2024 | NARAYAN CHANDRA SARKAR | 0.84 | 0 | 0 | 100
6 | COOCHBEHAR |  | Coochbehar Division | AGUMENTATION OF BASRAJA PRATHAM KHANDA PWSS | SM/16516 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000001/2025-2026 | 707/CD | 17/05/2025 | 15/08/2025 | M/S MAA MANASA CONSTRUCTION CO. | 24.21 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AGUMENTATION OF BASRAJA PRATHAM KHANDA PWSS | SM/16516 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000073/2025-2026 | 788/CD | 23/05/2025 | 21/08/2025 | SHREE RANI SATI ENTERPRISE | 75.53 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AGUMENTATION OF BASRAJA PRATHAM KHANDA PWSS | SM/16516 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000080/2025-2026 | 784/CD | 23/05/2025 | 21/08/2025 | GOUTAM KUMAR DAS | 92.33 | 0 | 0 | 0
Total | [13 empty] | 20336 | 0 | 0