## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | AGUMENTATION OF BASRAJA PRATHAM KHANDA PWSS | SM/16516 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AGUMENTATION OF BASRAJA PRATHAM KHANDA PWSS TW No.-I under NMDII, PHE.Dte,Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000948/2023-2024 | 2539/NMD-II | 16/08/2023 | 15/09/2023 | KAMAKHYA ENTERPRISE | 11.03 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AGUMENTATION OF BASRAJA PRATHAM KHANDA PWSS | SM/16516 | Augmentation | Execution of different works related to Aug. of Basraja Pratham Khanda PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000136/2023-2024 | 804/CD | 08/08/2023 | 05/01/2024 | AMBITIOUS ENTERPRISE | 336.6 | 71.05 | 21.11 | 60
3 | COOCHBEHAR |  | Coochbehar Division | AGUMENTATION OF BASRAJA PRATHAM KHANDA PWSS | SM/16516 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | AGUMENTATION OF BASRAJA PRATHAM KHANDA PWSS | SM/16516 | Augmentation | Charges for new service connection at Aug of Bashraja pratham khanda PWSS, P/H-III in the dist of Coochbehar. |  |  | BILL/00979/2024-2025 | BP-291/24-25 | 22/08/2024 |  | WBSEDCL | 6.18 | 0 | 0 | null
5 | COOCHBEHAR |  | Northern Mechanical Division II | AGUMENTATION OF BASRAJA PRATHAM KHANDA PWSS | SM/16516 | Augmentation | Charges for new service connection at Aug of Bashraja pratham khanda PWSS, P/H-III in the dist of Coochbehar. |  |  | BILL/00979/2024-2025 | BP-291/24-25 | 22/08/2024 |  | WBSEDCL | 6.18 | 0 | 0 | null
Total | [13 empty] | 20149.27 | 71.05 | 0.35