## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - IIBLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16517 | Augmentation | Execution of different works related to Aug. of MANTANI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000814/2022-2023 | 1993 | 28/03/2023 | 16/04/2025 | GOUTAM KUMAR DAS | 215.41 | 196.89 | 91.4 | 1
2 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - IIBLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16517 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT , TW No.- I under NMDII, PHE.Dte, Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000951/2023-2024 | 2540/NMD-II | 16/08/2023 | 15/09/2023 | HARAGOURI ENTERPRISE | 10.57 | 10.44 | 98.77 | 100
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - IIBLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16517 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000113/2023-2024 | 225/CD | 27/04/2023 | 27/04/2023 | Resource Division | 2.67 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - IIBLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16517 | Augmentation | QUOTATION FOR NSC AT MANTANI TW NO-I |  |  | BILL/02203/2023-2024 | BP-2023-24-467 | 07/12/2023 | 07/12/2023 | WBSEDCL | 5.18 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - IIBLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16517 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO (WITHIN MANTANI AREA) MANSAI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000586/2024-2025 | 2269/CD | 23/12/2024 | 21/02/2025 | GOUTAM KUMAR DAS | 54.91 | 0 | 0 | 60
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - IIBLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16517 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO (within area MANTANI JHINGAPUNI) SHILGHAGRI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000608/2024-2025 | 2309/CD | 23/12/2024 | 21/06/2025 | GOUTAM KUMAR DAS | 52.39 | 0 | 0 | 70
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - IIBLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16517 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000283/2025-2026 | 792/CD | 23/05/2025 | 21/08/2025 | ANIMESH DHAR CHOUDHURY | 32.79 | 0 | 0 | 0
8 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - IIBLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16517 | Augmentation | Supply & delivery of submersible pump-motor control starter at Mantani & adjacent w/s scheme in the district of Coochbehar within Coochbehar Mechanical Sub-division under Northern Mechanical Division-II P.H.E Dte. |  | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001374/2025-2026 | 1303/CMSD | 12/11/2025 | 22/11/2025 | DEY ENTERPRISE (BALLY) | 0.86 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - IIBLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16517 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000330/2025-2026 | 759/CD | 17/05/2025 | 13/11/2025 | M/S. MANDAL CONSTRUCTION | 32.05 | 0 | 0 | 50
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - IIBLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16517 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000284/2025-2026 | 793/CD | 23/05/2025 | 21/08/2025 | PALLAB BHAWAL | 30.52 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - IIBLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16517 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000286/2025-2026 | 795/CD | 23/05/2025 | 19/11/2025 | NORTH BENGAL CONSTRUCTION CO | 37.91 | 0 | 0 | 30
12 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - IIBLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16517 | Augmentation | Charges related to Energization work at Aug of Mantani PWSS, P/H-III under Coochbehar dist. |  |  | BILL/00601/2025-2026 |  | 28/05/2025 | 28/05/2025 | WBSEDCL | 4.85 | 0 | 0 | 0
Total | [13 empty] | 480.12 | 207.33 | 43.18