## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - IIBLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16517 | Augmentation | QUOTATION FOR NSC AT MANTANI TW NO-I |  |  | BILL/02203/2023-2024 | BP-2023-24-467 | 07/12/2023 |  | WBSEDCL | 5.18 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - IIBLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16517 | Augmentation | Execution of different works related to Aug. of MANTANI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000814/2022-2023 | 1993 | 28/03/2023 | 25/08/2023 | GOUTAM KUMAR DAS | 215.41 | 52.43 | 24.34 | 1
3 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - IIBLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16517 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT , TW No.- I under NMDII, PHE.Dte, Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000951/2023-2024 | 2540/NMD-II | 16/08/2023 | 15/09/2023 | HARAGOURI ENTERPRISE | 10.57 | 4.28 | 40.49 | 50
Total | [13 empty] | 231.16 | 56.71 | 24.53