## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED PHULBARI PART A PWSS | SM/16518 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGMENTATION OF GROUND WATER BASED PHULBARI PART A PWSS,TW No.-I and II under NMD-II,PHE.Dte,Alipurduar. |  |  | ORD/000944/2023-2024 | 2533/NMD-II | 16/08/2023 | 15/09/2023 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 22.01 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED PHULBARI PART A PWSS | SM/16518 | Augmentation | Execution of different works related to PHULBARI PART-A PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1366/1-5/NBC-1; Dt.: 28-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000657/2022-2023 | 1988/CD | 28/03/2023 | 25/08/2023 | SHREE RANI SATI ENTERPRISE | 369.93 | 159.91 | 43.23 | 36
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED PHULBARI PART A PWSS | SM/16518 | Augmentation | Execution of different works related to ANDARAN FULBARI PWSS under JAL JEEVAN MISSION PART Y | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000017/2023-2024 | 391/CD | 23/05/2023 | 22/06/2023 | SSPR VALVE MANUFACTURING PVT. LTD. | 69.66 | 0 | 0 | 48
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED PHULBARI PART A PWSS | SM/16518 | Augmentation | EXECUTION OF DIFFERENT WORK AT PHULBARI PART-A |  |  | BILL/02005/2023-2024 | BP-1167-P2 | 13/03/2024 |  | SHREE RANI SATI ENTERPRISE | 18 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED PHULBARI PART A PWSS | SM/16518 | Augmentation | EXECUTION OF DIFFERENT WORK AT ABUAR PATHAR PWSS |  |  | BILL/02068/2023-2024 | BP-1115 | 02/03/2024 |  | S & P ENTERPRISE | 152.3 | 0 | 0 | 0
Total | [13 empty] | 631.9 | 159.91 | 25.31