## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED BARASOLMARI-SINGIJANI PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16519 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGMENTATION OF GROUND WATER BASED BARASOLMARI-SINGIJANI PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT, TW No.- I and II under NMD-II,PHE.Dte,Alipurduar |  |  | ORD/000942/2023-2024 | 2536/NMD-II | 16/08/2023 | 15/09/2023 | MITRA ENTERPRISE | 21.11 | 0 | 0 | 0
2 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED BARASOLMARI-SINGIJANI PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16519 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT SINGIJANI TW I |  |  | BILL/00790/2024-2025 | BP-233/24-25 | 26/07/2024 | 26/07/2024 | WBSEDCL | 7.21 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARASOLMARI-SINGIJANI PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16519 | Augmentation | Execution of different works related to Aug. of BARASOLMARI-SINGIJANI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1370/1-5/NBC-1; Dt.: 28-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000674/2022-2023 | 1990/CD | 28/03/2023 | 26/08/2025 | GOUTAM KUMAR DAS | 373.73 | 277.36 | 74.21 | 40
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARASOLMARI-SINGIJANI PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16519 | Augmentation | Execution of different works related to MUKULDANGA, ANGARKATA PARADUBI & BARASOLMARI-SINGIJANI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000076/2024-2025 | 1186/CD | 18/06/2024 | 10/12/2025 | SHREE RANI SATI ENTERPRISE | 76.56 | 0 | 0 | 40
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARASOLMARI-SINGIJANI PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16519 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000074/2025-2026 | 789/CD | 23/05/2025 | 21/08/2025 | SHREE RANI SATI ENTERPRISE | 69.41 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARASOLMARI-SINGIJANI PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16519 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000261/2025-2026 | 775/CD | 17/05/2025 | 15/08/2025 | SANJAY MANDAL | 65.17 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARASOLMARI-SINGIJANI PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT | SM/16519 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000258/2025-2026 | 774/CD | 17/05/2025 | 19/02/2026 | SANKAR CHAKRABORTY | 45.33 | 0 | 0 | 97
Total | [13 empty] | 658.52 | 277.36 | 42.12