## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16520 | Augmentation | Constructions of 250 Cum OHR as per Departmental Design & drawing , Providing F.H.T.C ,New laying DI Pipe Line & other allied work at CHHAT RAMPUR PWSS under JAL JEEVAN MISSION (PART ¿D) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000217/2022-2023 | 706/CD | 27/08/2022 | 23/02/2023 | GOUTAM KUMAR DAS | 88.74 | 30.43 | 34.29 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16520 | Augmentation | Execution of different works related to CHHAT RAMPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000084/2023-2024 | 619/CD | 12/07/2023 | 04/01/2026 | GOUTAM KUMAR DAS | 329.26 | 258.63 | 78.55 | 20
3 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16520 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT, TW No.-I under NMD-II PHE DTE,APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000929/2023-2024 | 2526/NMD-II | 16/08/2023 | 15/09/2023 | M/S A.D. ENTERPRISE | 10.58 | 8.79 | 83.08 | 50
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16520 | Augmentation | Execution of different works related to CHHAT RAMPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000748/2022-2023 | 1832/CD | 09/03/2023 | 01/06/2025 | GOUTAM KUMAR DAS | 61.23 | 46.43 | 75.84 | 100
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16520 | Augmentation | EXECUTION OF DIFFERENT WORK AT JIRAN PUR PWSS |  |  | BILL/02072/2023-2024 | BP-1227-P1 | 22/03/2024 | 22/03/2024 | MALAY KR.DEB | 109.82 | 0 | 0 | 0
6 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16520 | Augmentation | Charges for new service connection at Chhatrampur PWSS, P/H-I in the dist of Coochbehar. |  |  | BILL/02019/2024-2025 | BP-434/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 6.52 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16520 | Augmentation | FUEL BILL |  |  | BILL/02075/2023-2024 | BP-1407 | 31/03/2024 | 31/03/2024 | R.C BANIK BANIK & SONS | 3.88 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16520 | Augmentation | FUEL BILL |  |  | BILL/02018/2023-2024 |  | 01/03/2024 | 01/03/2024 | A.O BSNL | 3.88 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/16520 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000096/2025-2026 | 748/CD | 17/05/2025 | 15/08/2025 | GOUTAM KUMAR DAS | 35.19 | 0 | 0 | 0
Total | [13 empty] | 649.11 | 344.28 | 53.04