## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -I PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16522 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 112/CD | 26/04/2023 | 26/04/2023 | Resource Division | 2.07 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -I PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16522 | Augmentation | Execution of different works related to DEWANHAT LAB area under GHARGHARIA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000783/2023-2024 | 664/CD | 11/03/2024 | 10/05/2024 | BHAGWATI BHUJEL | 6.94 | 6.84 | 98.65 | 100
3 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -I PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16522 | Augmentation | NEW SERVICE CONNECTION AT GHARGHARIA (AUG) ZONE-I, PH-I |  |  | BILL/00893/2024-2025 | BP-286/24-25 | 22/08/2024 | 22/08/2024 | WBSEDCL | 17.54 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -I PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16522 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -I PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT TW No.-I under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000933/2023-2024 | 2529/NMD-II | 16/08/2023 | 31/05/2025 | MASSK ENGINEERING WORKS | 11.03 | 0 | 0 | 95
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -I PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16522 | Augmentation | Execution of different works related to Aug. of GHARGHARIA PART-A PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000354/2023-2024 | 69/CD | 18/04/2023 | 07/05/2025 | AKANSHA COMMERCIAL PVT. LTD. | 173.04 | 0 | 0 | 30
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -I PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16522 | Augmentation | Execution of different works related to Aug. of GHARGHARIA PART-B PWSS under JAL JEEVAN MISSION PART A | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000089/2024-2025 | 1287/CD | 08/07/2024 | 04/04/2025 | M/S PALIT ENTERPRISE | 87.59 | 0 | 0 | 30
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -I PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16522 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000123/2025-2026 | 763/CD | 17/05/2025 | 15/08/2025 | AKANSHA COMMERCIAL PVT. LTD. | 68.77 | 0 | 0 | 30
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -I PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16522 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000100/2025-2026 | 729/CD | 17/05/2025 | 15/08/2025 | MS BIDYUT SARKAR | 23.91 | 0 | 0 | 0
Total | [13 empty] | 390.87 | 6.84 | 1.75