## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -II PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16523 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -II PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT TW No.I under NMD-II,PHE.Dte,Alipurduar. |  |  | ORD/001144/2023-2024 | 2888/NMD-II | 17/10/2023 | 16/11/2023 | SUBHASIS ROY | 11.03 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -II PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16523 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 114/CD | 26/04/2023 | 26/04/2023 | Resource Division | 4.14 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -II PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16523 | Augmentation | Execution of different works related to Aug. of GHARGHARIA PART-B PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000008/2023-2024 | 465/CD | 02/06/2023 | 30/01/2024 | M/S PALIT ENTERPRISE | 115.23 | 43.97 | 38.16 | 40
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -II PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16523 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO (WITHIN CHANDAMARI , GHARGHARIA ZONE-II , KURSHAMARI AREA) PHALIMARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000591/2024-2025 | 2275/CD | 23/12/2024 | 20/09/2025 | TAPAN CHANDA | 86.58 | 0 | 0 | 30
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -II PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16523 | Augmentation | Execution of different works related to Aug. of GHARGHARIA PART-B PWSS under JAL JEEVAN MISSION PART A | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000089/2024-2025 | 1287/CD | 08/07/2024 | 04/04/2025 | M/S PALIT ENTERPRISE | 87.59 | 0 | 0 | 30
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -II PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16523 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000082/2025-2026 | 691/CD | 15/05/2025 | 13/08/2025 | MATARA CONSTRUCTION CO. | 31.28 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -II PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/16523 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000287/2025-2026 | 796/CD | 23/05/2025 | 21/08/2025 | MS MAA ELECTRIC ELETRONIC | 14.22 | 0 | 0 | 0
Total | [13 empty] | 350.07 | 43.97 | 12.56