## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA MADHUSUDAN PWSS | SM/16524 | New | Material Requisition To Resource Division |  |  | RTOR000137/2023-2024 | 241/CD | 27/04/2023 | 27/04/2023 | Resource Division | 21.12 | 0 | 0 | 0
2 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | BARA MADHUSUDAN PWSS | SM/16524 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BARAMADHUSUDAN TW NO. I. |  |  | BILL/00521/2024-2025 | BP-176/24-25 | 03/07/2024 | 03/07/2024 | WBSEDCL | 11.12 | 0 | 0 | 0
3 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA MADHUSUDAN PWSS | SM/16524 | New | HIRING OF VEHICLE FOR AE FHTC PURPOSE |  |  | BILL/01454/2023-2024 | BP-950 | 31/01/2024 | 31/01/2024 | AJAD HOSSAIN | 0.55 | 0 | 0 | 0
4 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | BARA MADHUSUDAN PWSS | SM/16524 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BARAMADHUSUDAN TW NO. II |  |  | BILL/00277/2024-2025 | BP-76/24-25 | 16/05/2024 | 16/05/2024 | WBSEDCL | 3.77 | 0 | 0 | 0
5 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA MADHUSUDAN PWSS | SM/16524 | New | Execution of different works related to BARA MADHUSUDAN PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000140/2023-2024 | 806/CD | 08/08/2023 | 27/08/2025 | BRAJA GOPAL SAHA | 292.45 | 79.57 | 27.21 | 70
6 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | BARA MADHUSUDAN PWSS | SM/16524 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for BARA MADHUSUDAN PWSS , TW No.- I and II under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001145/2023-2024 | 2889/NMD-II | 17/10/2023 | 01/06/2025 | DAS CONSTRUCTION | 21.15 | 0 | 0 | 80
7 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA MADHUSUDAN PWSS | SM/16524 | New | Execution of different works related to BARA MADHUSUDAN PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000030/2024-2025 | 1139/CD | 14/06/2024 | 15/04/2025 | BRAJA GOPAL SAHA | 59.77 | 0 | 0 | 45
8 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA MADHUSUDAN PWSS | SM/16524 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000101/2025-2026 | 755/CD | 17/05/2025 | 15/08/2025 | RAJIB CHAKRABORTY | 23.55 | 0 | 0 | 0
Total | [13 empty] | 433.47 | 79.57 | 18.36