## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | Providing functional house hold tap connection within command area of PRAN MAJUMDER Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. (Part-B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000141/2022-2023 | 215/MTB | 26/07/2022 | 10/08/2022 | SANJAY MANDAL | 4.8 | 4.8 | 99.95 | 1
2 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | Providing functional house hold tap connection within command area of Pranmajumder Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. (Part-A) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000148/2022-2023 | 212/MTB | 26/07/2022 | 10/08/2022 | NORTHE BENGAL CONST CO | 4.69 | 4.69 | 100 | 1
3 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | Execution of different works related to Aug. of Pran Majumder PWSSunder JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000118/2023-2024 | 634/CD | 12/07/2023 | 09/12/2023 | SHRI ANNAPURNA DISTRIBUTORS | 218.17 | 206.13 | 94.48 | 70
4 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | Execution of different works related to PRAN MAJUMDER PWSS under JAL JEEVAN MISSION PART C | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000485/2023-2024 | 287/CD | 09/02/2024 | 28/10/2024 | SHRI ANNAPURNA DISTRIBUTORS | 96.22 | 94.28 | 97.98 | 100
5 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | Execution of different works related to PRAN MAJUMDER PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000607/2023-2024 | 657/CD | 11/03/2024 | 10/05/2024 | SHRI ANNAPURNA DISTRIBUTORS | 24.67 | 23.74 | 96.21 | 100
6 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | fuel bill |  |  | BILL/02049/2023-2024 | BP-1411 | 31/03/2024 | 31/03/2024 | R.C BANIK BANIK & SONS | 1.74 | 0 | 0 | 0
7 | COOCHBEHAR |  | Northern Mechanical Division II | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | Electric Quotation Bill for NSC at PRANMAJUMDER (AUG) |  |  | BILL/02236/2023-2024 | BP-2023-24-490 | 21/12/2023 | 21/12/2023 | WBSEDCL | 5.23 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | HIRING VEWHICLE FOR AE HQ |  |  | BILL/00596/2024-2025 | BP-231 | 01/08/2024 | 01/08/2024 | BHAGWATI BHUJEL | 0.77 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000289/2025-2026 | 79X8/CD | 23/05/2025 | 21/08/2025 | SWAPAN KUMAR ROY | 28.88 | 0 | 0 | 0
10 | COOCHBEHAR |  | Northern Mechanical Division II | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME TW No.-I under NMD-II,PHE.Dte,Alipurduar. |  |  | ORD/001134/2023-2024 | 2881/NMD-II | 17/10/2023 | 16/11/2023 | M/S. SAMRIDDHI ENTERPRISE | 11.69 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | Execution of different works related to PRAN MAJUMDER PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000426/2023-2024 | 1482/CD | 20/12/2023 | 01/07/2025 | SHRI ANNAPURNA DISTRIBUTORS | 96.67 | 31.57 | 32.66 | 66
12 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | Execution of different works related to PMAJUMDER & G CHOWRANGEE PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000550/2023-2024 | 608/CD | 11/03/2024 | 01/07/2025 | SHRI ANNAPURNA DISTRIBUTORS | 84.76 | 47.23 | 55.72 | 30
13 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000032/2025-2026 | 598/CD | 28/04/2025 | 27/07/2025 | SHRI ANNAPURNA DISTRIBUTORS | 72.86 | 0 | 0 | 30
14 | COOCHBEHAR |  | Coochbehar Division | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | SM/16525 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000033/2025-2026 | 599/CD | 28/04/2025 | 27/07/2025 | SHRI ANNAPURNA DISTRIBUTORS | 23.12 | 0 | 0 | 30
Total | [13 empty] | 674.27 | 412.44 | 61.17