## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Providing House connection for GHUGHUMARI PWSS under Cooch Behar Division. PHE Dte PART Z | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000068/2022-2023 | 265/CD | 24/05/2022 | 08/07/2022 | SWAPAN KR.SARKAR | 16.05 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 4th Site of GHUGHUMARI PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000449/2021-2022 | 1439/CD | 10/03/2022 | 09/04/2022 | TAPAN CHANDA | 10.7 | 0 | 0 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | laying of distribution line for FHTC under Ghughumari PWSS PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000157/2022-2023 | 197/SD | 27/06/2022 | 27/07/2022 | KRISHNA GOPAL BASK | 4.99 | 0 | 0 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Providing 150 nos F.H.T.C. for Ghughumari W.S.S. under Cooch Behar Sadar Sub- Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000108/2022-2023 | 198/SD | 27/06/2022 | 27/07/2022 | SWAPAN KR.SARKAR | 4.99 | 0 | 0 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Providing 150 nos. FHTC in Ghughumari (Part-B) Piped Water Supply Scheme under Cooch Behar Sadar Sub-Division, P.H.E.Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000139/2022-2023 | 202/SD | 27/06/2022 | 27/07/2022 | RED STAR UNEMPLOYED CO -OPARATIVE LABOUR CON.CONS.S LTD. | 4.81 | 0 | 0 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Providing 150 nos F.H.T.C. for Ghughumari (Part-C) W.S.S. under Cooch Behar Sadar Sub- Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000111/2022-2023 | 207/SD | 27/06/2022 | 27/07/2022 | SWAPAN SAHA | 4.82 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Providing 150 nos F.H.T.C. for Ghughumari (Part-A) W.S.S. under Cooch Behar Sadar Sub- Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000106/2022-2023 | 201/SD | 27/06/2022 | 27/07/2022 | SWAPAN KR.SARKAR | 4.82 | 0 | 0 | 1
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000066/2022-2023 | 1955/CD | 24/03/2023 | 24/03/2023 | Resource Division | 67.99 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000150/2023-2024 | 348/CD | 18/05/2023 | 18/05/2023 | Resource Division | 7.2 | 0 | 0 | 0
10 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | QUOTATION FOR NSC AT GHUGUMARI TW NO VII |  |  | BILL/01725/2023-2024 | BP-2023-24-318 | 27/09/2023 | 27/09/2023 | WBSEDCL | 6.31 | 0 | 0 | 0
11 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT GHUGUMARI PWSS TW -IV |  |  | BILL/00537/2022-2023 | CB-164/22-23 | 18/03/2023 | 18/03/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
12 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT GHUGHUMARI (AUG) TW NO-V |  |  | BILL/00158/2023-2024 | BP-2023-24-116 | 18/05/2023 | 18/05/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
13 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | QUOTATION FOR NSC AT GHUGUMARI TW NO VIII |  |  | BILL/01726/2023-2024 | BP-2023-24-319 | 27/09/2023 | 27/09/2023 | WBSEDCL | 6.74 | 0 | 0 | 0
14 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | QUOTATION FOR NSC AT GHUGUMARI TW NO VI |  |  | BILL/01722/2023-2024 | BP-2023-24-350 | 27/09/2023 | 27/09/2023 | WBSEDCL | 8.83 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Execution of different works related to GHUGHUMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000451/2022-2023 | 1427/CD | 29/12/2022 | 28/01/2023 | SWAPAN SAHA | 5.55 | 0 | 0 | 100
16 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Execution of different works related to GHUGHUMARI ZONE - II PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1340/1-5/NBC-1; Dt.: 24-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000567/2022-2023 | 1960/CD | 24/03/2023 | 21/03/2025 | MS BIDYUT SARKAR | 482.85 | 0 | 0 | 60
17 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Execution of different works related to GHUGHUMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000169/2023-2024 | 946/CD | 04/09/2023 | 25/02/2025 | MS BIDYUT SARKAR | 98.18 | 0 | 0 | 30
18 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Execution of different works related to GHUGHUMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000349/2023-2024 | 1333/CD | 24/11/2023 | 23/01/2024 | KARTICK CH SEAL | 9.96 | 0 | 0 | 60
19 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of GHUGHUMARI PWSS, TW no .IV in the district of Coochbehar under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000871/2022-2023 | 684/NMD-II | 28/03/2023 | 27/04/2023 | CHOWDHURY AND BASU ENTERPRISE | 11.25 | 0 | 0 | 100
20 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Ghugumari water supply scheme, TW no. V, VI and VII under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000674/2023-2024 | 2055/NMD-II | 26/07/2023 | 31/12/2024 | M/S SAJAHAN CHOWDHURY | 34 | 0 | 0 | 100
21 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Name of Work: Execution of different works related to GHUGHUMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000260/2023-2024 | 1027/CD | 22/09/2023 | 21/11/2023 | SWAPAN KR.SARKAR | 21.8 | 0 | 0 | 100
22 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Laying DI P/Line & other allied works related to GHUGHUMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000576/2023-2024 | 666/CD | 11/03/2024 | 09/06/2024 | SUBHAS CHANDRA ROY | 5.57 | 0 | 0 | 90
23 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | ADD, QTN FOR ELECTRICAL INFRA. DEV WORK AT GHUGUMARI (AUG) PWSS |  |  | BILL/00817/2024-2025 | BP-245/24-25 | 30/07/2024 | 30/07/2024 | WBSEDCL | 7.35 | 0 | 0 | 0
24 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | EXECUTION OF DIFFERENT WORK AT JIRAN PUR PWSS |  |  | BILL/02072/2023-2024 | BP-1227-P1 | 22/03/2024 | 22/03/2024 | MALAY KR.DEB | 109.82 | 0 | 0 | 0
25 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Execution of different works related to GHUGHUMARI ZONE-I PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1289/1-5/NBC-1; Dt.: 17-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000632/2022-2023 | 1903/CD | 17/03/2023 | 13/03/2025 | MS BIDYUT SARKAR | 389.87 | 0 | 0 | 82
26 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Execution of different works (Within Area of DHALUABARI) related to GHUGHUMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000338/2023-2024 | 1322/CD | 24/11/2023 | 22/05/2024 | SWAPAN SAHA | 9.18 | 0 | 0 | 40
27 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
28 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation OF Ghugumari Water Supply Scheme TW No.-VIII under Jal Jeevan Mission NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000511/2024-2025 | 2649/NMD-II | 09/12/2024 | 08/01/2025 | CHOWDHURY AND BASU ENTERPRISE | 11.04 | 0 | 0 | 90
29 | COOCHBEHAR |  | Coochbehar Division | Augmentation of GHUGHUMARI Piped Water Supply Scheme | SM/16531 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO TUPAMARI DEWANBAS HARI BHANGA GHUGHUMARI & DUDHERKUTHI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000568/2024-2025 | 2287/CD | 23/12/2024 | 22/04/2025 | MS SSB CONSTRUCTION CO | 66.53 | 0 | 0 | 30
Total | [13 empty] | 21202.6 | 0 | 0