## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 184/CD | 27/04/2023 | 27/04/2023 | Resource Division | 14.9 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | Execution of different works related to JORE SIMULI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1313/1-5/NBC-1; Dt.: 20-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000612/2022-2023 | 1932/CD | 22/03/2023 | 19/08/2023 | M/S KAMAK ENGINEERS AND CO | 619.31 | 278.72 | 45.01 | 85
3 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | Execution of different works related to JORE SIMULI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000320/2023-2024 | 1303/CD | 24/11/2023 | 22/02/2024 | UDAY CHAKI | 4.92 | 4.74 | 96.32 | 96
4 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | Material Requisition To Resource Division |  |  | RTOR000164/2023-2024 | 21/CD | 05/01/2024 | 05/01/2024 | Resource Division | 19.88 | 0 | 0 | 0
5 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT JORESIMULI TW II. |  |  | BILL/00641/2024-2025 | BP-160/24-25 | 21/06/2024 | 21/06/2024 | WBSEDCL | 3.1 | 0 | 0 | 0
6 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT JORESIMULI TW I. |  |  | BILL/00517/2024-2025 | BP-118/24-25 | 24/05/2024 | 24/05/2024 | WBSEDCL | 3.75 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Jore Simuli water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001087/2023-2024 | 2787/NMD-II | 06/10/2023 | 05/11/2023 | A.S. ENTERPRISE | 21.65 | 0 | 0 | 80
8 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | Execution of different works related to JORE SIMULI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000365/2023-2024 | 1362/CD | 05/12/2023 | 28/01/2025 | M/S KAMAK ENGINEERS AND CO | 96.35 | 40.4 | 41.93 | 75
9 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
10 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | Execution of different works with in SHIKARPUR area related to JORE SIMULI PWSS under JAL JEEVAN MISSION MTB | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000026/2024-2025 | 1711/CD | 25/09/2024 | 24/11/2024 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 25.02 | 0 | 0 | 80
11 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | JORE SIMULI PIPED WATER SUPPLY SCHEME | SM/16541 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000288/2025-2026 | 797/CD | 23/05/2025 | 21/08/2025 | MA MAHAMAYA UNP. CO-OP LABOUR CONT & CONT SOCITY LTD. | 24 | 0 | 0 | 0
Total | [13 empty] | 20622.19 | 323.86 | 1.57