## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Bajejama Chilakhana ZONE-I PWSS | SM/16931 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Bajejama Chilakhana Water Supply Scheme TW No.- I & II of Zone-I under NMD-II,PHE.Dte,Apd. |  |  | ORD/000680/2023-2024 | 2115/NMD-II | 27/07/2023 | 26/08/2023 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 21.03 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Bajejama Chilakhana ZONE-I PWSS | SM/16931 | Augmentation | Execution of different works related to BAJEJAMA CHILAKHANA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000411/2023-2024 | 1314/CD | 24/11/2023 | 23/01/2024 | GOUTAM KUMAR DAS | 4.32 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Bajejama Chilakhana ZONE-I PWSS | SM/16931 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 148/CD | 27/04/2023 | 27/04/2023 | Resource Division | 16.95 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Bajejama Chilakhana ZONE-I PWSS | SM/16931 | Augmentation | Execution of different works related to (with in B Chilakhana Z1) DEOCHARAI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000480/2023-2024 | 283/CD | 09/02/2024 | 09/04/2024 | SANJAY MANDAL | 17.98 | 0 | 0 | 100
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Bajejama Chilakhana ZONE-I PWSS | SM/16931 | Augmentation | Execution of different works related to JHAUKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000521/2023-2024 | 319/CD | 09/02/2024 | 09/04/2024 | M/S PRADIP KUMAR PAL | 58.32 | 0 | 0 | 100
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Bajejama Chilakhana ZONE-I PWSS | SM/16931 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Bajejama Chilakhana ZONE-I PWSS | SM/16931 | Augmentation | Execution of different works related to B.CHILAKHANA 1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000555/2023-2024 | 648/CD | 11/03/2024 | 28/03/2025 | SSPR VALVE MANUFACTURING PVT. LTD. | 91.98 | 0 | 0 | 50
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Bajejama Chilakhana ZONE-I PWSS | SM/16931 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO Natabari Bajejama Chilakhana ZONE-I Chhatoa PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000546/2024-2025 | 2231/CD | 23/12/2024 | 20/08/2025 | AASHIRBAD ENTERPRISE | 27.56 | 0 | 0 | 80
Total | [13 empty] | 20027.42 | 0 | 0