## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | Maidam Piped Water Supply Scheme | SM/16981 | New | New service connection at Maidam PWSS, P/H-II |  |  | BILL/02324/2023-2024 | BP-2023-24-541 | 17/01/2024 | 17/01/2024 | WBSEDCL | 4.33 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | Maidam Piped Water Supply Scheme | SM/16981 | New | New service connection at Maidam PWSS, P/H-I |  |  | BILL/02323/2023-2024 | BP-2023-24-540 | 17/01/2024 | 17/01/2024 | WBSEDCL | 15.58 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | Maidam Piped Water Supply Scheme | SM/16981 | New | QUOTATION FOR NSC AT MAIDAM TW NO II |  |  | BILL/02459/2023-2024 |  | 16/01/2024 | 16/01/2024 | WBSEDCL | 4.33 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | Maidam Piped Water Supply Scheme | SM/16981 | New | QUOTATION FOR NSC AT MAIDAM TW NO I |  |  | BILL/02460/2023-2024 |  | 16/01/2024 | 16/01/2024 | WBSEDCL | 15.58 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-II | Coochbehar Division | Maidam Piped Water Supply Scheme | SM/16981 | New | Execution of different works related to MAIDAM PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000515/2023-2024 | 313/CD | 09/02/2024 | 08/05/2025 | KHOKAN DAS | 43.13 | 36.13 | 83.77 | 100
6 | COOCHBEHAR | Dinhata-II | Coochbehar Division | Maidam Piped Water Supply Scheme | SM/16981 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000094/2025-2026 | 735/CD | 17/05/2025 | 15/08/2025 | GHOSH AND SAHA CONSTRUCTION | 46.77 | 0 | 0 | 0
7 | COOCHBEHAR | Dinhata-II | Coochbehar Division | Maidam Piped Water Supply Scheme | SM/16981 | New | Execution of different works related to AUG of MAIDAM PWSS under JAL JEEVAN MISSION . | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000004/2023-2024 | 49/CD | 17/04/2023 | 11/05/2025 | KHOKAN DAS | 200.29 | 149.94 | 74.86 | 95
8 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | Maidam Piped Water Supply Scheme | SM/16981 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components alongwith Cu wound line voltage corrector for Rejuvenation of MAIDAM water supply scheme,TW no I AND II under JJM under NMD-II, PHE Dte.APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000940/2023-2024 | 2545/NMD-II | 16/08/2023 | 01/03/2025 | M/S SAJAHAN CHOWDHURY | 21.15 | 15.24 | 72.05 | 100
Total | [13 empty] | 351.18 | 201.3 | 57.32