## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Execution of different works related to BALABHUT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000790/2022-2023 | 1866/CD | 14/03/2023 | 13/04/2023 | M/S BADAL CH SAHA | 28.46 | 22.32 | 78.41 | 80
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Execution of different works related to Aug of BALABHUT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000006/2023-2024 | 50/CD | 17/04/2023 | 06/05/2025 | M/S. MANDAL CONSTRUCTION | 123.68 | 86.32 | 69.79 | 75
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Execution of different works related to CHHOTO GODAIKHORA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000066/2023-2024 | 403/CD | 23/05/2023 | 22/06/2023 | RAHAMAN ENTERPRISE | 0 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Execution of different works related to BALABHUT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000076/2023-2024 | 4400/CD | 31/05/2023 | 30/07/2023 | M/S. MANDAL CONSTRUCTION | 32.22 | 18.95 | 58.8 | 58
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Execution of different works related to WSS under JAL JEEVAN MISSION |  |  | ORD/000772/2023-2024 | 123 | 05/12/2023 | 03/02/2024 | BAKUL DUTTA | 0 | 0 | 0 | 0
6 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Balabhut Water Supply Scheme TW No.I under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000921/2023-2024 | 2506/NMD-II | 14/08/2023 | 30/04/2025 | GEETA CONSTRUCTION | 9.88 | 7.9 | 80 | 100
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Execution of different works related to Balabhut PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000073/2024-2025 | 1716/CD | 25/09/2024 | 24/12/2024 | GOUTAM KUMAR DAS | 3.41 | 0 | 0 | 100
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO (within BALABHUT area) BOXIRHAT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000628/2024-2025 | 2235/CD | 23/12/2024 | 21/02/2025 | RAJIB CHAKRABORTY | 6.96 | 0 | 0 | 25
9 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Charges for new service connection at Balabhut PWSS, P/H-III in the dist of Coochbehar. |  |  | BILL/01652/2024-2025 | BP-408/24-25 | 20/11/2024 | 20/11/2024 | WBSEDCL | 6.05 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000088/2025-2026 | z24 | 05/07/2025 | 03/10/2025 | NORTH BENGAL CONSTRUCTION CO | 37.91 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | EXECUTION OF DIFFERENT WORKS (within CHARALJANI area) RELATED TO BALABHUT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000670/2024-2025 | 99/CD | 17/01/2025 | 12/01/2026 | M/S. MANDAL CONSTRUCTION | 27.08 | 0 | 0 | 99
13 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Supply, delivery and installation of 15 KVA servo motor operated Copper wound line voltage corrector at BALABHUT Water Supply Scheme, TW No.-l in the dist coochbehar,562/NMD-II,08-03-2019, RA-II & F |  |  | BILL/02403/2024-2025 |  | 28/01/2025 | 28/01/2025 | MALAY KUMAR SAHA | 0.61 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000109/2026-2027 | 20203 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000120/2026-2027 | 20214 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000121/2026-2027 | 20215 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000124/2026-2027 | 20218 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000107/2026-2027 | 20101 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000108/2026-2027 | 20202 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000116/2026-2027 | 20210 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000110/2026-2027 | 20204 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
22 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000111/2026-2027 | 20205 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
23 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000113/2026-2027 | 20207 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
24 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000117/2026-2027 | 20211 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
25 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000118/2026-2027 | 20212 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
26 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000043/2026-2027 | 20041 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
27 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000047/2026-2027 | 20045 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
28 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000051/2026-2027 | 20049 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
29 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000054/2026-2027 | 20052 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
30 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000055/2026-2027 | 20053 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
31 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000056/2026-2027 | 20024 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
32 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000057/2026-2027 | 20025 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
33 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000059/2026-2027 | 20054 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
34 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000060/2026-2027 | 20055 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
35 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000061/2026-2027 | 20056 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
36 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000064/2026-2027 | 20059 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
37 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000065/2026-2027 | 20060 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
38 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000066/2026-2027 | 20061 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
39 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000071/2026-2027 | 20066 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
40 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000072/2026-2027 | 20067 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
41 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000073/2026-2027 | 20068 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
42 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000074/2026-2027 | 20069 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
43 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000075/2026-2027 | 20070 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
44 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000076/2026-2027 | 20071 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
45 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000079/2026-2027 | 20074 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
46 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000080/2026-2027 | 20075 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
47 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000081/2026-2027 | 20076 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
48 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000082/2026-2027 | 20077 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
49 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000083/2026-2027 | 20078 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
50 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000084/2026-2027 | 20079 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | NAN | 0
51 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000085/2026-2027 | 20080 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
52 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000086/2026-2027 | 20080 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
53 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000087/2026-2027 | 20081 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
54 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000088/2026-2027 | 20082 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
55 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000094/2026-2027 | 20088 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
56 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000095/2026-2027 | 20089 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
57 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000098/2026-2027 | 20092 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
58 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000099/2026-2027 | 20093 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
59 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000033/2026-2027 | 20031 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
60 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000037/2026-2027 | 20035 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
61 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000041/2026-2027 | 20039 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
62 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000027/2026-2027 | 20025 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
63 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000028/2026-2027 | 20026 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
64 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000029/2026-2027 | 20027 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
65 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000030/2026-2027 | 20028 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
66 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000031/2026-2027 | 20029 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
67 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000032/2026-2027 | 20030 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
68 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000112/2026-2027 | 20206 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
69 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000114/2026-2027 | 20208 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
70 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000115/2026-2027 | 20209 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
71 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000119/2026-2027 | 20213 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
72 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000122/2026-2027 | 20216 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
73 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000123/2026-2027 | 20217 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
74 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000125/2026-2027 | 20219 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
75 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000126/2026-2027 | 20220 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
76 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000127/2026-2027 | 20221 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
77 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | 1st Extension of Additional Work for Providing Sanitary and Water Supply Arrangement to the Temporary Establishement for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID NIS Code: 10008651Location: RAMKRISHNA BOYS HIGH SCHOOL, COOCH BEHAR :: Requisition Type: Additional Case Ref. Requisition ID: 10002263: Camp Start Date: 16/04/26: Camp End Date: 30/04/26" |  |  | ORD/000128/2026-2027 | 726(HQ)/CD | 16/04/2026 | 01/05/2026 | BIJOY ROY | 0.7 | 0 | 0 | 0
78 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000129/2026-2027 | 20223 | 01/05/2026 | 08/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
79 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | 3rd Extension of Providing Sanitary and Water Supply Arrangement to the Temporary Establishement for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID NIS Code: 10002042Location: Hostel of Nagar Dakaliganj High School :: Camp Start Date: 15/04/26: Camp End Date: 29/04/26 |  |  | ORD/000004/2026-2027 | xyz(HQ)/CD | 15/04/2026 | 30/04/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | NAN | 0
80 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000024/2026-2027 | 20022 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
81 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000089/2026-2027 | 20083 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
82 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000090/2026-2027 | 20084 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
83 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000091/2026-2027 | 20085 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
84 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000092/2026-2027 | 20086 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
85 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000093/2026-2027 | 20087 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
86 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000096/2026-2027 | 20090 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
87 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000097/2026-2027 | 20091 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
88 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000100/2026-2027 | 20094 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
89 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | "You will have to abide by all terms & conditions as laid down/submitted by your end in B.F. 2911 / (i) (ii) within 7(Seven) Days. The work should be taken up at once in consultation with the below mentioned Assistant Engineer & should be completed within stipulated time from the date of issue this Order, failing which penalty clauses 2 & 3 as laid down B.F. 2911 / (i) (ii) will be applied. The name & specimen signature of your agent or agents who may be present at the work site or may receive material from store on your behalf should be furnished in legal document immediately on the receipt of Work Order." |  |  | ORD/000101/2026-2027 | 20095 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
90 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000102/2026-2027 | 20096 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
91 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000103/2026-2027 | 20097 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
92 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000104/2026-2027 | 20098 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
93 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000105/2026-2027 | 20099 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
94 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000106/2026-2027 | 20100 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
95 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000036/2026-2027 | 20034 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
96 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000039/2026-2027 | 20037 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
97 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000040/2026-2027 | 20038 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
98 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000045/2026-2027 | 20043 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
99 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000046/2026-2027 | 20044 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
100 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000048/2026-2027 | 20046 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
101 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000050/2026-2027 | 20048 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
102 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000068/2026-2027 | 20063 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
103 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000069/2026-2027 | 20064 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
104 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000070/2026-2027 | 20065 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
105 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000077/2026-2027 | 20072 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
106 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000078/2026-2027 | 20073 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
107 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000009/2026-2027 | 20009 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
108 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000013/2026-2027 | 200013 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
109 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000014/2026-2027 | 20013 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
110 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000015/2026-2027 | 20014 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
111 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000017/2026-2027 | 20016 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
112 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000020/2026-2027 | 20019 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
113 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000025/2026-2027 | 20023 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
114 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000026/2026-2027 | 20024 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
115 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000005/2026-2027 | 20005 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
116 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000008/2026-2027 | 20008 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
117 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000010/2026-2027 | 20010 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
118 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000011/2026-2027 | 200011 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
119 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000012/2026-2027 | 20012 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
120 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000023/2026-2027 | 20021 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
121 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000007/2026-2027 | 20007 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
122 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000016/2026-2027 | 20015 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | NAN | 0
123 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000018/2026-2027 | 20017 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
124 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000019/2026-2027 | 20018 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
125 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000021/2026-2027 | 20020 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
126 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000022/2026-2027 | 20020 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
127 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000042/2026-2027 | 20040 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
128 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000044/2026-2027 | 20042 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
129 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000049/2026-2027 | 20047 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
130 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000052/2026-2027 | 20050 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
131 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000053/2026-2027 | 20051 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
132 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000034/2026-2027 | 20032 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
133 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000035/2026-2027 | 20033 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
134 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000038/2026-2027 | 20036 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
135 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000058/2026-2027 | 20026 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
136 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000062/2026-2027 | 20057 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
137 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000063/2026-2027 | 20058 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
Total | [13 empty] | 332.67 | 135.48 | 40.73