## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Execution of different works related to BALABHUT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000790/2022-2023 | 1866/CD | 14/03/2023 | 13/04/2023 | M/S BADAL CH SAHA | 28.46 | 0 | 0 | 80
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Execution of different works related to CHHOTO GODAIKHORA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000066/2023-2024 | 403/CD | 23/05/2023 | 22/06/2023 | RAHAMAN ENTERPRISE | 0 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Execution of different works related to BALABHUT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000076/2023-2024 | 4400/CD | 31/05/2023 | 30/07/2023 | M/S. MANDAL CONSTRUCTION | 32.22 | 0 | 0 | 58
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Execution of different works related to WSS under JAL JEEVAN MISSION |  |  | ORD/000772/2023-2024 | 123 | 05/12/2023 | 03/02/2024 | BAKUL DUTTA | 0 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
6 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Charges for new service connection at Balabhut PWSS, P/H-III in the dist of Coochbehar. |  |  | BILL/01652/2024-2025 | BP-408/24-25 | 20/11/2024 | 20/11/2024 | WBSEDCL | 6.05 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000088/2025-2026 | z24 | 05/07/2025 | 03/10/2025 | NORTH BENGAL CONSTRUCTION CO | 37.91 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Execution of different works related to Aug of BALABHUT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000006/2023-2024 | 50/CD | 17/04/2023 | 06/05/2025 | M/S. MANDAL CONSTRUCTION | 123.68 | 0 | 0 | 75
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Execution of different works related to Balabhut PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000073/2024-2025 | 1716/CD | 25/09/2024 | 24/12/2024 | GOUTAM KUMAR DAS | 3.41 | 0 | 0 | 100
10 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | SM/17439 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Balabhut Water Supply Scheme TW No.I under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000921/2023-2024 | 2506/NMD-II | 14/08/2023 | 30/04/2025 | GEETA CONSTRUCTION | 9.88 | 0 | 0 | 100
Total | [13 empty] | 297.32 | 0 | 0