## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF Chhota Godaikhora Pwss | SM/17443 | Augmentation | Laying of HDPE pipe line for distribution system incl culvert bridge crossing with DI/GI pipe & other Misc works at CHHOTO GADAIKHORA PWSS under Cooch Behar Division. PHE Dte. PART 5 (B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000097/2021-2022 | 323/CD | 13/08/2021 | 27/09/2021 | MATARA CONSTRUCTION CO. | 21.35 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF Chhota Godaikhora Pwss | SM/17443 | Augmentation | Trial run for distribution system under Chotto Gadaikhora PWSS under Mathabhanga Sub-Division PHE Dte. (Period from 01/01/2022 to 28/02/2022) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000400/2021-2022 | 873/CD | 23/12/2021 | 23/12/2022 | TAPAN CHANDA | 0.95 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF Chhota Godaikhora Pwss | SM/17443 | Augmentation | Laying of HDPE pipe line for distribution system incl culvert bridge crossing with DI/GI pipe & other Misc works at CHHOTO GADAIKHORA PWSS under Cooch Behar Division. PHE Dte. PART 5 (A) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000129/2021-2022 | 324/CD | 13/08/2021 | 27/09/2021 | MS BIDYUT SARKAR | 21.36 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF Chhota Godaikhora Pwss | SM/17443 | Augmentation | Providing House connection for CHHOTO GADAIKHORA PWSS under Cooch Behar Division. PHE Dte. P 1 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000330/2021-2022 | 1231/CD | 09/02/2022 | 11/03/2022 | TAPAN CHANDA | 17.55 | 0 | 0 | 1
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF Chhota Godaikhora Pwss | SM/17443 | Augmentation | Providing House connection for CHHOTO GADAIKHORA PWSS under Cooch Behar Division. PHE Dte. P 2 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000349/2021-2022 | 1250/CD | 09/02/2022 | 11/03/2022 | ASHIM KUMAR CHAKRABORTY | 14.03 | 0 | 0 | 1
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF Chhota Godaikhora Pwss | SM/17443 | Augmentation | Providing functional house hold tap connection within command area of Chhoto Godaikhora Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte.(Part-C) Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000055/2022-2023 | 48/MTB | 02/05/2022 | 09/05/2022 | ARUN KUMAR KARMAKAR | 4.84 | 0 | 0 | 1
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF Chhota Godaikhora Pwss | SM/17443 | Augmentation | Providing 150nos functional house hold tap connection within command area of Chhoto Godaikhora Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte.(Part-D) Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000056/2022-2023 | 49/MTB | 02/05/2022 | 09/05/2022 | MS DD ENTERPRISE | 4.84 | 0 | 0 | 1
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF Chhota Godaikhora Pwss | SM/17443 | Augmentation | Providing functional house hold tap connection within command araa under Choto Gadaikhora Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000140/2022-2023 | 126/MTB | 23/06/2022 | 08/07/2022 | SANJAY MANDAL | 4.81 | 0 | 0 | 1
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF Chhota Godaikhora Pwss | SM/17443 | Augmentation | Execution of different works related to Aug. of CHHOTA GADAIKHORA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000040/2023-2024 | 466/CD | 02/06/2023 | 30/10/2023 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 115.52 | 0 | 0 | 60
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF Chhota Godaikhora Pwss | SM/17443 | Augmentation | Execution of different works related to CHHOTO GODAIKHORA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000042/2023-2024 | 403CD | 23/05/2023 | 20/10/2023 | SAIMONS CONTRACT AND CONSTRUCTION CO | 8.02 | 0 | 0 | 100
11 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF Chhota Godaikhora Pwss | SM/17443 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT CHHOTA GODAIKHORA TW NO. III. |  |  | BILL/00280/2024-2025 | BP-78/24-25 | 16/05/2024 | 16/05/2024 | WBSEDCL | 5.27 | 0 | 0 | 0
12 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF Chhota Godaikhora Pwss | SM/17443 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Chhota Godaikhora Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000925/2023-2024 | 2503/NMD-II | 14/08/2023 | 02/03/2025 | MUSTAFI CONCERN | 10.53 | 0 | 0 | 80
Total | [13 empty] | 229.07 | 0 | 0