## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/18093 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 144/CD | 27/04/2023 |  | Resource Division | 11.66 | 0 | 0 | 0
2 | COOCHBEHAR |  | Northern Mechanical Division II | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/18093 | Augmentation | NEW SERVICE CONNECTION CHARGES AT CHAKCHAKA ZONE-II, PH-II |  |  | BILL/02739/2023-2024 | BP-2023-24-610 | 16/02/2024 |  | WBSEDCL | 6.31 | 0 | 0 | null
3 | COOCHBEHAR |  | Northern Mechanical Division II | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/18093 | Augmentation | NEW SERVICE CONNECTION AT CHAKCHAKA ZONE-II, PH-I |  |  | BILL/02737/2023-2024 | BP-2023-24-611 | 16/02/2024 |  | WBSEDCL | 5.38 | 0 | 0 | null
4 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/18093 | Augmentation | Laying DI P/Line & other allied works related to CHAKCHAKA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000577/2023-2024 | 617/CD | 11/03/2024 | 10/05/2024 | M/S. MANDAL CONSTRUCTION | 14.77 | 0 | 0 | 30
5 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/18093 | Augmentation | Execution of different works related to Aug. of CHAKCHAKA ZONE - II PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 163/1-5/NBC-1; Dt.: 18-05-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000010/2023-2024 | 395/CD | 23/05/2023 | 20/10/2023 | SWAPAN KR.SARKAR | 204.49 | 43.77 | 21.41 | 22
6 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/18093 | Augmentation | Execution of different works related to (within TAKAGACH area) CHAKCHAKA ZONE II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000341/2023-2024 | 1325/CD | 24/11/2023 | 23/01/2024 | SWAPAN KR.SARKAR | 31.8 | 0 | 0 | 70
7 | COOCHBEHAR |  | Northern Mechanical Division II | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/18093 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Chakchaka Water Supply Scheme TW No.-I and II of Zone-II under NMD-II,PHE.Dte,,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001082/2023-2024 | 2779/NMD-II | 05/10/2023 | 04/11/2023 | MUSTAFI CONCERN | 21.07 | 0 | 0 | 80
Total | [13 empty] | 295.48 | 43.77 | 14.81