## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/18093 | Augmentation | Execution of different works related to Aug. of CHAKCHAKA ZONE - II PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 163/1-5/NBC-1; Dt.: 18-05-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000010/2023-2024 | 395/CD | 23/05/2023 | 18/11/2025 | SWAPAN KR.SARKAR | 204.49 | 154.03 | 75.33 | 22
2 | COOCHBEHAR |  | Northern Mechanical Division II | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/18093 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Chakchaka Water Supply Scheme TW No.-I and II of Zone-II under NMD-II,PHE.Dte,,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001082/2023-2024 | 2779/NMD-II | 05/10/2023 | 04/11/2023 | MUSTAFI CONCERN | 21.07 | 19.49 | 92.5 | 80
3 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/18093 | Augmentation | Execution of different works related to (within TAKAGACH area) CHAKCHAKA ZONE II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000341/2023-2024 | 1325/CD | 24/11/2023 | 23/01/2024 | SWAPAN KR.SARKAR | 31.8 | 31.56 | 99.25 | 70
4 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/18093 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 144/CD | 27/04/2023 | 27/04/2023 | Resource Division | 11.66 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/18093 | Augmentation | FABRICATION AND INSTALLATION OF LAND POSSESSION SIGN BOARD AT EVERY LANDS OF DIFFERENT PWSS WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, PHE Dte. UNDER JJM (PART-C) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000623/2024-2025 | 2325/CD | 23/12/2024 | 21/02/2025 | ISLAMPUR SWARNADEEP SOCIETY | 44.29 | 0 | 0 | 100
6 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/18093 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO SAJHERPAR KHATALBARI CHAKCHAKA ZONE II MARANADIRKUTHI & GOPALPUR PWSS UNDER JAL JEEVAN MISSION. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000533/2024-2025 | 2217/CD | 23/12/2024 | 20/08/2025 | MATARA CONSTRUCTION CO. | 80.28 | 0 | 0 | 80
7 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/18093 | Augmentation | Laying DI P/Line & other allied works related to CHAKCHAKA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000577/2023-2024 | 617/CD | 11/03/2024 | 09/05/2025 | M/S. MANDAL CONSTRUCTION | 14.77 | 14.41 | 97.51 | 30
8 | COOCHBEHAR |  | Northern Mechanical Division II | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/18093 | Augmentation | NEW SERVICE CONNECTION AT CHAKCHAKA ZONE-II, PH-I |  |  | BILL/02737/2023-2024 | BP-2023-24-611 | 16/02/2024 | 16/02/2024 | WBSEDCL | 5.38 | 0 | 0 | 0
9 | COOCHBEHAR |  | Northern Mechanical Division II | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/18093 | Augmentation | NEW SERVICE CONNECTION CHARGES AT CHAKCHAKA ZONE-II, PH-II |  |  | BILL/02739/2023-2024 | BP-2023-24-610 | 16/02/2024 | 16/02/2024 | WBSEDCL | 6.31 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | SM/18093 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION |  |  | ORD/000036/2025-2026 | 721/CD | 17/05/2025 | 15/08/2025 | BIJOY ROY | 16.73 | 0 | 0 | 0
Total | [13 empty] | 436.78 | 219.48 | 50.25