## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER HEMKUMARI ZONE-I ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/18122 | Augmentation | Execution of different works related to HALDIBARI (M) Z-I PWSS under COB DIVN PHED | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000819/2022-2023 | 1857/CD | 14/03/2023 | 13/04/2023 | DAS ENTERPRISE | 9.01 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER HEMKUMARI ZONE-I ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/18122 | Augmentation | Execution of different works related to HALDIBARI (M) Z-I PWSS under COB DIVN PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000797/2022-2023 | 1848/CD | 14/03/2023 | 13/04/2023 | SANJAY MANDAL | 9.01 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER HEMKUMARI ZONE-I ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/18122 | Augmentation | Execution of different works related to HEMKUMARI Z1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000074/2023-2024 | 411/CD | 23/05/2023 | 22/06/2023 | UDAY CHAKI | 9.16 | 8.06 | 87.92 | 95
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER HEMKUMARI ZONE-I ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/18122 | Augmentation | VEHICLE FUEL FOR tfg SUB DIVISION, PHED |  |  | BILL/00950/2023-2024 | BP-470 | 01/09/2023 |  | SUCHITRO FUEL STATION | 0.41 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER HEMKUMARI ZONE-I ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/18122 | Augmentation | VEHICLE FOR AE RWS |  |  | BILL/00952/2023-2024 | BP-486 | 18/09/2023 |  | AJAD HOSSAIN | 0.18 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER HEMKUMARI ZONE-I ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/18122 | Augmentation | VEHICLE FOR AE/RWS |  |  | BILL/00951/2023-2024 | BP-485 | 18/09/2023 |  | AJAD HOSSAIN | 0.18 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER HEMKUMARI ZONE-I ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/18122 | Augmentation | VEHICLE FOR AE/MTB |  |  | BILL/00953/2023-2024 | BP-492 | 21/09/2023 |  | NARAYAN CHANDRA SARKAR | 0.22 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER HEMKUMARI ZONE-I ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/18122 | Augmentation | Execution of different works related to HEMKUMARI Z1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000093/2023-2024 | 628/CD | 12/07/2023 | 09/12/2023 | UNIBRO INFRASERV PRIVATE LIMITED | 304.96 | 92.56 | 30.35 | 35
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER HEMKUMARI ZONE-I ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/18122 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER HEMKUMARI ZONE-I ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/18122 | Augmentation | Execution of different works related to HALDIBARI BLOCK AND GAJENDRAPUR CHOWRINGHEE PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000045/2024-2025 | 1153/CD | 14/06/2024 | 13/08/2024 | AASHIRBAD ENTERPRISE | 65.7 | 0 | 0 | 30
Total | [13 empty] | 20188.13 | 100.61 | 0.5