## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME | SM/18133 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BHERBHERI MANABARI TW III. |  |  | BILL/00522/2024-2025 | BP-117/24-25 | 24/05/2024 | 24/05/2024 | WBSEDCL | 3.41 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME | SM/18133 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BHERBHERI MANABARI TW II. |  |  | BILL/00515/2024-2025 | BP-116/24-25 | 24/05/2024 | 24/05/2024 | WBSEDCL | 4.38 | 0 | 0 | 0
3 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME | SM/18133 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BHERBHERI MANABARI TW I. |  |  | BILL/00516/2024-2025 | BP-115/24-25 | 24/05/2024 | 24/05/2024 | WBSEDCL | 4.17 | 0 | 0 | 0
4 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME | SM/18133 | New | Execution of different works related to BHEBHERI MANABARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000088/2023-2024 | 623/CD | 12/07/2023 | 31/07/2025 | SUPER TECH ENGINEERS CO- OPERATIVE SPOCY.LTD | 250.29 | 169.93 | 67.89 | 70
5 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME | SM/18133 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for BHERBHERI MANABARI water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000981/2023-2024 | 2612/NMD-II | 25/08/2023 | 16/05/2025 | M/S SAJAHAN CHOWDHURY | 22.28 | 0 | 0 | 80
6 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME | SM/18133 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
7 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME | SM/18133 | New | EXECUTION OF DIFFERENT WORKS (within PHULBARI PART A & BHERBHERI MANABARI area) RELATED TO TAKOAMARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000666/2024-2025 | 95/CD | 17/01/2025 | 12/01/2026 | ORIENTAL CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 38.98 | 0 | 0 | 70
8 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME | SM/18133 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
9 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME | SM/18133 | New | Yard lighting arrangement at Head Work Site for Different PWSS (BALASI and others) under JJM in the BLOCK: Mathabhanga-I, DISTRICT: Coochbehar under NMD-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000139/2025-2026 | 1348/NMD-II | 19/06/2025 | 19/07/2025 | S.K ENTERPRISE | 34.38 | 0 | 0 | 0
10 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME | SM/18133 | New | ADDITIONAL MANUAL QUOTATION DUE TO SHIFTING OF SITE FROM BHERBHERI MANABARI PHE III TO KHARIJA KAWARDARA PHE II. |  |  | BILL/02163/2024-2025 | BP-466/24-25 | 21/01/2025 | 21/01/2025 | WBSEDCL | 3.67 | 0 | 0 | 0
11 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME | SM/18133 | New | ADDITIONAL ELECTRIC QUOTATION FOR ROUTE CHANGE AT BHERBHERI MANABARI TW II. |  |  | BILL/02035/2024-2025 | BP-451/24-25 | 09/01/2025 | 09/01/2025 | WBSEDCL | 6.32 | 0 | 0 | 0
12 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME | SM/18133 | New | Solarization of grid connected pumping installation at Different PWSS at Mathabhanga-I Block in the dist.of Coochbehar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000167/2025-2026 | 1388/NMD-II | 26/06/2025 | 24/09/2025 | E AND C ENGINEERING & CONSULTANCY SERVICES PRIVATE LIMITED | 47.89 | 0 | 0 | 30
Total | [13 empty] | 20693.12 | 169.93 | 0.82