## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME | SM/18133 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for BHERBHERI MANABARI water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. |  |  | ORD/000981/2023-2024 | 2612/NMD-II | 25/08/2023 | 24/09/2023 | M/S SAJAHAN CHOWDHURY | 22.28 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME | SM/18133 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BHERBHERI MANABARI TW I. |  |  | BILL/00516/2024-2025 | BP-115/24-25 | 24/05/2024 |  | WBSEDCL | 4.17 | 0 | 0 | null
3 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME | SM/18133 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BHERBHERI MANABARI TW II. |  |  | BILL/00515/2024-2025 | BP-116/24-25 | 24/05/2024 |  | WBSEDCL | 4.38 | 0 | 0 | null
4 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME | SM/18133 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BHERBHERI MANABARI TW III. |  |  | BILL/00522/2024-2025 | BP-117/24-25 | 24/05/2024 |  | WBSEDCL | 3.41 | 0 | 0 | null
5 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME | SM/18133 | New | Execution of different works related to BHEBHERI MANABARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000088/2023-2024 | 623/CD | 12/07/2023 | 09/12/2023 | SUPER TECH ENGINEERS CO- OPERATIVE SPOCY.LTD | 250.29 | 44.04 | 17.6 | 70
6 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | BHERBHERI MANABARI PIPED WATER SUPPLY SCHEME | SM/18133 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20073.81 | 44.04 | 0.22