## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | GROUND WATER BASED BHURUKULDANGA PIPED WATER SUPPLY SCHEME | SM/18134 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for BHURKULDANGA Water Supply Scheme TW No.- I AND II of Zone-I under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001066/2023-2024 | 2730/NMD-II | 25/09/2023 | 25/10/2023 | RMD TRADING | 22.28 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | GROUND WATER BASED BHURUKULDANGA PIPED WATER SUPPLY SCHEME | SM/18134 | New | Execution of different works related to BHURKULDANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000079/2023-2024 | 605/CD | 10/07/2023 | 07/12/2023 | CHAKRABORTY ENTERPRISE. | 0 | 0 | 0 | 0
3 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | GROUND WATER BASED BHURUKULDANGA PIPED WATER SUPPLY SCHEME | SM/18134 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BHURKULDANGA TW I. |  |  | BILL/00635/2024-2025 | BP-157/24-25 | 21/06/2024 |  | WBSEDCL | 5.58 | 0 | 0 | null
4 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | GROUND WATER BASED BHURUKULDANGA PIPED WATER SUPPLY SCHEME | SM/18134 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BHURKULDANGA TW II. |  |  | BILL/00636/2024-2025 | BP-158/24-25 | 21/06/2024 |  | WBSEDCL | 3.98 | 0 | 0 | null
5 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | GROUND WATER BASED BHURUKULDANGA PIPED WATER SUPPLY SCHEME | SM/18134 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BHURKULDANGA TW II. |  |  | BILL/00636/2024-2025 | BP-158/24-25 | 21/06/2024 |  | WBSEDCL | 3.98 | 0 | 0 | null
6 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | GROUND WATER BASED BHURUKULDANGA PIPED WATER SUPPLY SCHEME | SM/18134 | New | Execution of different works related to BHURKULDANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000121/2023-2024 | 637/CD | 12/07/2023 | 09/12/2023 | CHAKRABORTY ENTERPRISE. | 155.19 | 34.35 | 22.14 | 80
Total | [13 empty] | 191 | 34.35 | 17.99