## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | GROUND WATER BASED BHURUKULDANGA PIPED WATER SUPPLY SCHEME | SM/18134 | New | Execution of different works related to BHURKULDANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000079/2023-2024 | 605/CD | 10/07/2023 | 07/12/2023 | CHAKRABORTY ENTERPRISE. | 0 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | GROUND WATER BASED BHURUKULDANGA PIPED WATER SUPPLY SCHEME | SM/18134 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for BHURKULDANGA Water Supply Scheme TW No.- I AND II of Zone-I under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001066/2023-2024 | 2730/NMD-II | 25/09/2023 | 25/10/2023 | RMD TRADING | 22.28 | 19.81 | 88.91 | 100
3 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | GROUND WATER BASED BHURUKULDANGA PIPED WATER SUPPLY SCHEME | SM/18134 | New | Execution of different works related to BHURKULDANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000121/2023-2024 | 637/CD | 12/07/2023 | 07/11/2025 | CHAKRABORTY ENTERPRISE. | 155.19 | 127.03 | 81.85 | 100
4 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | GROUND WATER BASED BHURUKULDANGA PIPED WATER SUPPLY SCHEME | SM/18134 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (within BHURUKULDANGA arae) AMBARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION |  | ORD/000609/2024-2025 | 2310/CD | 23/12/2024 | 21/02/2025 | ASHIM KUMAR CHAKRABORTY | 75.87 | 0 | 0 | 0
5 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | GROUND WATER BASED BHURUKULDANGA PIPED WATER SUPPLY SCHEME | SM/18134 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (within DUAI SUAI & BHURUKULDANGA area) KHARIJA KHAWARDARA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000618/2024-2025 | 2319/CD | 23/12/2024 | 19/08/2025 | KAJAL KUMAR DE | 72.8 | 0 | 0 | 50
6 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | GROUND WATER BASED BHURUKULDANGA PIPED WATER SUPPLY SCHEME | SM/18134 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BHURKULDANGA TW I. |  |  | BILL/00635/2024-2025 | BP-157/24-25 | 21/06/2024 | 21/06/2024 | WBSEDCL | 5.58 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | GROUND WATER BASED BHURUKULDANGA PIPED WATER SUPPLY SCHEME | SM/18134 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BHURKULDANGA TW II. |  |  | BILL/00636/2024-2025 | BP-158/24-25 | 21/06/2024 | 21/06/2024 | WBSEDCL | 3.98 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | GROUND WATER BASED BHURUKULDANGA PIPED WATER SUPPLY SCHEME | SM/18134 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
9 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | GROUND WATER BASED BHURUKULDANGA PIPED WATER SUPPLY SCHEME | SM/18134 | New | Yard lighting arrangement at Head Work Site for Different PWSS (BALASI and others) under JJM in the BLOCK: Mathabhanga-I, DISTRICT: Coochbehar under NMD-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000139/2025-2026 | 1348/NMD-II | 19/06/2025 | 19/07/2025 | S.K ENTERPRISE | 34.38 | 0 | 0 | 0
10 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | GROUND WATER BASED BHURUKULDANGA PIPED WATER SUPPLY SCHEME | SM/18134 | New | Solarization of grid connected pumping installation at Different PWSS at Mathabhanga-I Block in the dist.of Coochbehar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000167/2025-2026 | 1388/NMD-II | 26/06/2025 | 24/09/2025 | E AND C ENGINEERING & CONSULTANCY SERVICES PRIVATE LIMITED | 47.89 | 0 | 0 | 30
Total | [13 empty] | 906.04 | 146.84 | 16.21